## Sheet1
Annex 9 - Timetable for Calls for Proposals - example template
Programme name:
Call publication number:
|  |  | 1st CfP | 2nd CfP | 2016 | [7 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019
| TASK | Days | Tentative start dates |  | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
| JMC Meeting | 1 | 2023-06-01 | bar: 2016 J; 2017 F; 2017 J; 2018 J; 2018 S; 2019 J; 2019 J
CALL | Publication of the call for proposal | 45 | 2023-09-16 | 2025-09-15 | bar: 2016 S; 2018 S
| Partner search forum |  | 2023-08-15 | 2023-08-15 | bar: 2016 A to 2016 S; 2018 A to 2018 S
| Organising info sessions |  | 2023-09-23 | 2023-09-23 | bar: 2016 S; 2018 S
EVALUATION | Step 1: Opening & administrative checks | 45 | 2023-10-31 | 2025-10-30 | bar: 2016 N; 2018 N
| Step 1: Assessment of concept notes | 90 | 2024-01-29 | 2026-01-28 | bar: 2016 N to 2017 J; 2018 N to 2019 J
| Step 2: Assessement of full applications | 45 | 2024-03-14 | 2026-03-14 | bar: 2017 M to 2017 A; 2019 M to 2019 A
| Step 3: Verification of eligibility | 60 | 2024-05-13 | 2026-05-13 | bar: 2017 M; 2019 M
| Final Approval Evaluation (CBCS, DEU, JMC) | 30 | 2024-06-12 | 2026-06-12 | bar: 2017 J; 2019 J
| Budgetary clearing & contracting | 60 | 2024-08-11 | 2026-08-11 | bar: 2017 J to 2017 A; 2019 J to 2019 A
MONITORING | Training for beneficiaries | 7 | 2024-08-18 | 2026-08-18 | bar: 2017 A; 2019 A
| Kick-off event |  | 2024-09-07 | 2026-09-07 | bar: 2017 S; 2019 S
| Monitoring GS Projects |  | Throughout | Throughout | bar: 2017 S to 2019 D
| Preparation of the AIR | 60 | 1 December each year | bar: 2016 D to 2017 J; 2017 D to 2018 J; 2018 D to 2019 J; 2019 D
Notes
It is proposed that partner search forums will be held before the publication of the CfPs
It is proposed that all CfPs are restricted and not open
It is proposed that the same assessors will examine both concept notes and full applications
Formulas:
Tentative start dates = [Tentative start dates, row above]+C13
Tentative start dates = [Tentative start dates, row above]+20