ANNEX 6: List of strategic projects under the 2007-2013 IPA CBC programmes

| **Contracting Authority** | **Tender reference number** | **Project /Action Title** | **IPA CBC Programme** | **Type of Contract (TA, Grant, Works, Services/Supply, Strategic Projects)** | **Awarded Contractor** | **Status** | **Total EU grant** |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Government of ME** (Ministry of Interior and Directorate for Public Works in ME) | N/A | Preparation of design documentation for works for BCP Hani i Hotit – Božaj and BCP Grabom – Zatrijebačka Cijevna (Service contracts / co-financing from Montenegro) | AL-ME | Services  (one year) | Čovjek i Prostor, Ltd. | Completed | Government of ME co-financing contribution: € 70 000 |
| **DEU in ME** | 136608 | Reconstruction of the Border Crossing Point Božaj | AL-ME | Works | **Cancelled** on 17/08/2015 and relaunched on 29 February 2016 as lot 1 of the tender 137509 |  |  |
| **DEU in ME** coordinated with the Ministry of Interior of ME. | 137509 | Construction Works for Border Crossing Points Božaj and Cijevna | AL-ME | Works  (Lot 1: 12 months  Lot 2: 8 months) | Lot 1: Reconstruction of the Border Crossing Point Božaj: BREGU sh.a., Tirana (AL)  Lot 2: Construction of the Border Crossing Point Cijevna: PNP-Perošević d.o.o. – Bijelo Polje | Lot 1: Works started on 17 October 2016  Lot 2: Works to start on 30 January 2017 after the building permit was issued on 19 January 2017 | Lot 1: € 992 129.70  Lot 2: €  451 076.90 |
| **DEU in ME** coordinated with the Ministry of Interior of ME. | Framework contract | Supervision of the works at the BCPs in Božaj and Cijevna | AL-ME | Services  (25/5/2015-14/8/2018) | Institut za Građevinarstvo Podgorica | Under course | € 84 000 |
| **Government of ME** (Ministry of Interior) | N/A | Supply of equipment for BCPs in Montenegro | AL-ME | Supplies | N/A | Tender to be launched when the works will have been finished | Government of ME co-financing contribution: €200 000 |
| **Government of AL** (Border Police) | N/A | Supply of equipment for Shkodra Lake demarcation and control in Albania | AL-ME | Supplies | ??? | ??? | Government of AL co-financing contribution: € 270 000 |
| **DEU in AL** | 136751 | Construction of road Grabom – CBP with Montenegro | AL-ME | Works  (12 months, starting on 05/10/2015) | JV 2T SH.P.K.(AL) | Completed by 05/10/2016 | € 823 014.47 |
| **DEU in AL** | Framework contract | Supervision of the works for the road Grabom – CBP with Montenegro | AL-ME | Services  (25 months, from 28/09/2015 to 27/10/2017) | THC | Under course | € 89 000  (The allocation earmarked for works and supervision was € 1.3 million; they managed to contract € 912 014.47, entailing a loss of funds of € 487 985.53) |
| **EU Office in Kosovo[[1]](#footnote-1)** | 137981 | Construction of road Dragash/Kosovo – Shishtavec/Albania | AL-XK | Works  (8 months) | RSM COMPANY SHPK  (no 377-037 & 377-038) | Under course | € 888 395.68 |
| **EU Office in Kosovo** | Framework contract | Project design and supervision of works (construction of road Dragash/Kosovo-Shishtavec/Albania) | AL-XK | Services | INFRA plus | ??? | € 107 500 |
| **Government of Kosovo** | N/A | Construction of road Dragash/Kosovo – Shishtavec/Albania | AL-XK | ??? | ??? | ??? | € 130,254.36 |
| **DEU in AL** | 137241 | Construction of the road Shishtavec – BCP and internal roads in Shishtavec  (Shishtavec – BCP: 1.2 km, while 2.2 km of internal roads at Shishtavec) | AL-XK | Works  (start 01/12/2015 and end after extension 31/07/2017) | VEGA  (no 2015/366 824 & 2015/367 009) | Under course, only 30% of the envisaged works were completed after one year of implementation. | € 575 539.23  (2012-2013 allocations???) |
| **DEU in AL** | Framework contract | Supervision of the works in Shishtavec | AL-XK | Services | Contract no. 2015/368 917 | Under course | € 80 300 |
| **DEU in RS** | 135520 | Strengthening the capacity of the sector for emergency management in the field of unexploded ordnance (UXO) and other hazardous materials.  Lot 1: Survey equipment and supporting vehicles  Lot 2 Clothing, personnel protective equipment and miscellaneous. | HR-RS | Supplies  (19 months) | Lot 1: Advertout d.o.o. (RS)  Lot 2: Advertout d.o.o. (RS) | Under course (???) | Lot 1: € 793 240.00  Lot 2: € 39 077.00  (the total value of the operation could have reached € 1 058 823.53, including € 158 823.53 of co-financing to buy a specialised UXO vehicle) |
| **EU Office in XK** | ??? | Joint building in the new joint border crossing Point Stanqiq-Bella Novce (???) | MK-XK | Works (???) | ??? | ??? but not under implementation | €  1 200 000.00 (???)  (co-financing ???) |
| **EU Office in XK** | ??? | Joint building in the new joint border crossing Point Stanqiq-Bella Novce: Advanced draft of the concept design for further procedures | MK-XK | Service (???) | De Gressi Architects ??? | Under course ??? | €  (???)  (co-financing ???) |
| **DEU in RS** | Framework contract | Development of Municipal Waste Water Collection and Treatment in Bajina Basta | RS-BA | Technical assistance – service contract  (12 months) | A.R.S. Progetti S.P.A. | Completed | € 172 500.00 |
| **DEU in RS** | Framework contract | Identification and development of a secure data transfer system between information systems used in the IPA cross-border programme Serbia-Bosnia and Herzegovina | RS-BA | Technical assistance – service contract  (6 months) | Astec Global Consulting | Completed | € 42 550.00 |
| **DEU in RS** | 136838 | Joint Forest fire monitoring and suppression in Western Serbia – Monitoring equipment | RS-BA | Supplies | Lot 1 | Cancelled |  |
| **DEU in RS** | 136838 | Joint Forest fire monitoring and suppression in Western Serbia – Fire fighting vehicle | RS-BA | Supplies  (6 months + 6 months) | Lot 2: Avto Engineering Holding Group | Under course | € 247 764.00  (plus € 43 723.05 as 15 % of estimated co-financing to buy four specialised field vehicles) |
| **DEU in RS** | 136838 | Joint Forest fire monitoring and suppression in Western Serbia – Specialised equipment and hand tools | RS-BA | Supplies  (6 months) | Lot 3: Bexing d.o.o. (RS) | Under course | € 14 105.00 |
| **DEU in RS** | Framework contract | Preparation of technical documentation for construction of a tunnel under Kadinjaca Mountain (beneficiary Municipality Bajina Basta) | RS-BA | Technical assistance – service contract  (21 months) | Project Biro Utiber | Completed | € 129 750.00  (plus € 22 897.00 as 15 % of estimated co-financing) |
| **DEU in RS** | Framework contract 2012/289398 | Support to the Development of Ponikve Airport in Užice | RS-BA | Technical assistance – service contract (36 months) | ALAnet Global | Completed | € 157 238.00  (plus € 27 747.88 as the 15 % estimated co-financing) |

1. This designation is without prejudice to positions on status, and is in line with UNSCR 1244 and the ICJ Opinion on the Kosovo declaration of independence. [↑](#footnote-ref-1)