## General Overview
PROPOSAL OF A MONITORING TEMPLATE | [6 empty] | Formula to calculate Project Quality
MONITORING VISIT REPORT | [6 empty] | 67.8571 | 0 | >75% = High Quality
Project Information | [7 empty] | 1 | <=50% and >=75% = Medium Quality
Contract title: | [7 empty] | 0 | >50% and >=25% = Low Quality
Grant Beneficiary: | [7 empty] | FALSE
Project partners, incl. CBC partners:
Contract number:
Project duration:
Project start date:
Progress or interim report(s) received (date):
Project monitoring visits (date, venue and month of implementation):
Project's performance level: | 57 | / | 84 | Medium quality
Circulation Sheet
Step | Name and Surname |  |  |  | Submission Date | Signature
JTS TM in charge
Head of JTS (to endorse)
Programme Managers at OSs (for information)
Contracting Authorities TMs (for information)
Overview of the monitoring visit

## Checklist
| Question number | Specific question to be addressed | Comments | Overall performance | Recommendations |  |  |  |  | Serious deficiencies
|  |  |  | Serious deficiencies | [5 empty] | Improvements needed
|  |  |  | Improvement needed | [5 empty] | Satisfactory
|  |  |  | Satisfactory | [5 empty] | Very good
|  |  |  | Very good | [5 empty] | Not applicable
Not applicable
1. RELEVANCE
| 1.1 | Are the objectives of the intervention still responding to target groups’ needs/priorities as at the moment of submitting the project? |  | Serious deficiencies |  | 0 | 1 | 0 | 0 | 0
| 1.2 | Is the level of project relevance according to other elements still significant? |  | Improvements needed |  | 0 | 0 | 2 | 0 | 0
|  |  | ASSESSMENT | Improvements needed |  | 0 | 1 | 2 | 0 | 0 | 3 | 8 | 0.375
2. DESIGN
| 2.1 | Is the project well designed, with activities' complexity, duration and timing well defined, balanced and commensurate to beneficiaries' capacity? |  | Very good |  | 0 | 0 | 0 | 0 | 4
| 2.2 | Is the project logic well defined and reflected in a good logframe, with SMART indicators, and adequate targets? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 2.3 | Are OVIs realistic and likely to be achieved and are measurable? |  | Serious deficiencies |  | 0 | 1 | 0 | 0 | 0
| 2.4 | Has the project appropriate support by the local/regional stakeholders (local field situation)? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 2.5 | Are the risk analysis/ preconditions/ assumptions of the project comprehensive and relevant? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
|  |  | ASSESSMENT | Satisfactory |  | 0 | 1 | 0 | 9 | 4 | 14 | 20 | 0.7
3. EFFICIENCY
| 3.1 | Are the activities being implemented in line with the description of the action, including the timetable of activities/action plan? |  | Not applicable |  | 4 | 0 | 0 | 0 | 0
| 3.2 | Are activities being implemented within the budget envisaged? |  | Not applicable |  | 4 | 0 | 0 | 0 | 0
| 3.3 | Were all partners adequately involved in the realization of the action? |  | Not applicable |  | 4 | 0 | 0 | 0 | 0
| 3.4 | Where applicable, were cross-border partners adequately involved/consulted in the realization of the action? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 3.5 | If there have been changes in the timetable of activities or action plan, do the changes seem reasonable? |  | Very good |  | 0 | 0 | 0 | 0 | 4
| 3.6 | How well these changes have been managed? |  | Not applicable |  | 4 | 0 | 0 | 0 | 0
| 3.7 | Is it likely that all activities will be completed by the end of the period of implementation? |  | Serious deficiencies |  | 0 | 1 | 0 | 0 | 0
| 3.8 | Have the staff involved in the project sufficient capacity (both in terms of quantity and quality) to manage the project? |  | Improvements needed |  | 0 | 0 | 2 | 0 | 0
| 3.9 | Do the beneficiaries have a logical, consistent, regular and reliable system for monitoring project activities and outputs? |  | Not applicable |  | 4 | 0 | 0 | 0 | 0
| 3.10 | Is the project management making active use of the logframe and/or of other project management tools? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 3.11 | Are the outputs of the project delivered as planned (quantity/quality)? |  | Not applicable |  | 4 | 0 | 0 | 0 | 0
| 3.12 | Have the outputs been made available to the target group? |  | Not applicable |  | 4 | 0 | 0 | 0 | 0
|  |  | ASSESSMENT | Satisfactory |  | 28 | 1 | 2 | 6 | 4 | 13 | 20 | 0.65
4. EFFECTIVENESS
| 4.1 | Are the outcomes of the project being achieved as expected? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 4.2 | How are target groups assessing the quality and usefulness of the outcomes? |  | Improvements needed |  | 0 | 0 | 2 | 0 | 0
| 4.3 | As presently implemented, what is the likelihood that the project purpose will be achieved? |  | Very good |  | 0 | 0 | 0 | 0 | 4
| 4.4 | Is the progress on achievement of project indicators satisfactory up to date? |  | Not applicable |  | 4 | 0 | 0 | 0 | 0
|  |  | ASSESSMENT | Satisfactory |  | 4 | 0 | 2 | 3 | 4 | 9 | 12 | 0.75
5. IMPACT & CROSS-BORDER EFFECT
| 5.1 | Does it appear likely that the attainment of the project purpose will have an impact on the overall goal of the action? |  | Not applicable |  | 4 | 0 | 0 | 0 | 0
| 5.2 | Will the project contribute to the Programme indicators? |  | Not applicable |  | 4 | 0 | 0 | 0 | 0
| 5.3 | To what extent does/will the operation have any indirect (positive/negative) impact? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 5.4 | Is the project planned as: (a) a genuine joint project, (b) a mirror - same group of activities on each side of the border, or (c) a formalistic partnership - different types of activities with minor CB effect? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 5.5 | Are most of the activities jointly carried out with impact on both sides of the border? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 5.6 | Has the action a positive impact on the programme (e.g. any improvement at thematic sector level or local/regional CB area)? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 5.7 | Is the CBC programme recognized by beneficiaries as a tool for improvement of cooperation? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 5.8 | Is the CBC programme recognized by the beneficiaries as a tool for improvement in a thematic sector (in line with Programme measures)? |  | Not applicable |  | 4 | 0 | 0 | 0 | 0
|  |  | ASSESSMENT | Satisfactory |  | 12 | 0 | 0 | 15 | 0 | 15 | 20 | 0.75
6. SUSTAINABILITY
| 6.1 | How sustainable will be the transfer of project ownership (taking into account any hand-over strategy, the standing of the end recipient(-s) of project benefits/results, the experience within the project/related to project-content, staffing and other factors to be identified on a case by case basis)? |  | Not applicable |  | 4 | 0 | 0 | 0 | 0
| 6.2 | Will benefits/results of the project continue to be generated/used after its completion? |  | Not applicable |  | 4 | 0 | 0 | 0 | 0
| 6.3 | By whom, how and to what extent will further financing of benefits/results be ensured? |  | Not applicable |  | 4 | 0 | 0 | 0 | 0
| 6.4 | Are there other additional elements fostering sustainability (e.g. policy aspects, institutional capacity, social inclusion, environmental considerations, etc.)? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 6.5 | Where applicable, is the cross-border cooperation between the beneficiaries and their partners likely to continue after the end of the project implementation? |  | Not applicable |  | 4 | 0 | 0 | 0 | 0
|  |  | ASSESSMENT | Satisfactory |  | 16 | 0 | 0 | 3 | 0 | 3 | 4 | 0.75
[7 empty] | Total: |  |  |  | 57 | 84

## Main Findings
1. Relevance |  |  |  | 3 | / | 8
2. Design |  |  |  | 14 | / | 20
3. Efficiency |  |  |  | 13 | / | 20
4 Effectiveness |  |  |  | 9 | / | 12
5 Impact & Cross-border Effect |  |  |  | 15 | / | 20
6 Sustainability |  |  |  | 3 | / | 4
Project visit total score: | 57 | / | 84
Key points/ findings:
Key points/ findings:
Key points/ findings:
Key points/ findings:
Key points/ findings:
Key points/ findings: