Hierarchical Relations between the JTS and other Relevant Programme Structures

Rationale

Under IPA II cross-border programmes the technical assistance priority is implemented through service contracts awarded to a consortium or partnership established between the operating structures of two beneficiaries participating in the programme. During the programming process, upon the initiative of the EC, beneficiary countries for each cross-border programme reached an agreement on which country would have to host the contracting authority (hereinafter: CA). Every country ended up hosting the CA for at least one cross-border programme. The operating structure (OS) of the country where the CA is located concludes the technical assistance service contract (TASC) with the relevant Delegation of the European Union (DEU). This OS is directly responsible for the implementation of the TASC, including transfer of funds to the partner country OS, as well as the eligibility of all costs incurred under the TASC. The implementation of the TASC is supervised by the DEU of the country where the CA is located.

In indirect management, the operating structure of the country entrusted with budget implementation tasks for a given cross-border cooperation programme shall also include a CA. This means that for these countries the function of the CA is performed by a state body, usually a department of the Ministry of Finance, referred to as the Central Finance and Contracting Unit (CFCU). In this context, the DEU on behalf of the European Commission (EC) performs ex-ante control on grant award and procurement procedures (tendering and contracting) and ex-post control on contracts and grants under these cross-border programmes.

The main purpose of the TASC is to finance operations of the programme’s Joint Technical Secretariat (JTS), as detailed in the JTS Manual. Therefore, the majority of technical and practical matters related to the implementation of the TASC is carried out by the JTS staff and subsequently checked, approved and endorsed by other programme bodies, i.e. the OS responsible for implementation of TASC (which has to coordinate approval circuits with the partner country OS in many situations), the JMC, the CFCU and the DEU that is the CA for the TASC regardless of the management mode.

Taking into account the complexity of this situation, it was necessary to set the procedures that would describe the

- lines of communication,

- reporting obligations,

- delegation of tasks and

- supervision

between the JTS and the OS (i.e. CBC body and Contracting Authority in indirect management), and between the Head of the OS and the DEU.

General Principles

- Taking into account the most important aspects of a CBC programme implementation, the relations among different programme bodies are logically divided into two main categories:

  - Technical Assistance Service Contract:

The primary aspect of this category is efficiency, effectiveness and regularity of the implementation of TASC. This includes tasks from Section B of the JTS Manual: Managing Technical Assistance.

  - CBC programme implementation:

The primary aspect of this category is efficiency and effectiveness of the implementation of CBC programme, excluding the TA priority. This includes tasks from Sections E-H of the JTS Manual.

Many tasks described in Sections E-H of the JTS Manual relate to both categories, i.e. when programme implementation related matters have consequences on the TASC expenditures (e.g. the CA in indirect management is requesting an action from the JTS that will have a financial repercussion on the budget of the TASC).

Given the number of bodies involved and variety of tasks that need to be done, the following basic principles should be respected:

- Each body should appoint one person that will be the primary contact point for each category of relation.

For category I of communication, the contact person should be knowledgeable in technical issues related to the implementation of the TASC. The logical choice would fall onto a person dealing with finance/administration.

For category II of communication, the contact person should have the relevant experience and knowledge as well as a deep insight in all details of the implementation of the CBC programme for which he or she has been appointed.

It is quite acceptable that functions referred to shall be performed by the same person, i.e. there will be one contact point per institution and programme regardless of the category of communication involved.

- Depending on the contents of the communication, contact points of concerned bodies shall always be copied, regardless of who the initiator of the communication in question is. Please refer to the table at the beginning of each section of the JTS Manual for the list of concerned bodies for each task.

- Regardless of the contents of the communication, the contact point in the OS of the country where the CA is located (or the CBC body in the case of indirect management) as well as the Head of JTS shall always be copied (or informed in case of oral communication), subject to the confidentiality rules applicable.

- Whenever the JTS communicates with any of the programme bodies, the contact point in the OS of the country where the CA is located will always be copied (or informed in case of oral communication).

- When referring to communication between two bodies, it shall be understood that the nominated contact points for the relevant category of communication have communicated. The contact point for the JTS is always its Head, unless otherwise set in the internal communication procedures of the JTS.

A	Direct Management

The relations among bodies responsible for implementation of a cross-border programme under direct management is presented in Graph 1.

Graph 1: Organisational structure of programme bodies in direct management

CA for grants and the TASC

Country B

Strategic decisions

Partner in the TASC

Day-to-day implementation of the TASC

Contractor for the TASC

Country A

(where the CA is located)

Interested in success of the programme. Member of the TASC SC

OS

DEU

DEU

JTS

Antenna

OS

JMC Chair

JMC

1a

2

3

2a

1

3a

5

4

6

The left-hand side of the graph presents the structures in country A, where the CA is located, whereas on the right-hand side the programme structures in country B – the partner country – are presented.

Programme bodies are presented by rounded rectangles in different colours, depending on the type of the body; the programme bodies in country B are displayed in a lighter colour, because they are the partners and their responsibility for programme implementation under IPA II is little less significant than that of the programme bodies in the country A (leader) where the CA is located. The major role of each body is indicated within the respective callouts.

Connections between the bodies present possible lines of communication between them. Arrows indicate possible directions of the communications. Please note that all communications are bi-directional. Lines of communication in country B are dashed because of their relative significance. Each line of communication is labelled with a number. These numbers are used as references when describing the communications in the text and tables below.

Note that the JMC is presented by a large transparent rounded rectangle with dashed outline that represents the communication line with other programme bodies (line number 6). This rectangle representing the JMC overlaps partially with all other bodies since all bodies have their representatives in the JMC. There is no individual communication between any of the bodies with the JMC, as the communication is done either through official JMC meetings where all bodies are present, or through written procedure that always includes all bodies.

Table 1: Category I (TASC related) relations between programme bodies under direct management

| Line of comm. | Description | Anticipated frequency of comm. | Body with “higher authority” | Reporting provisions (type - frequency) |
| --- | --- | --- | --- | --- |
| 1 | JTS - OS. The OS is the contractor for the TASC which is used for financing operations of the JTS; therefore each action undertaken by the JTS by default requires the prior approval from the OS, especially when costs are being involved. Communication goes both ways since tasks can be initiated either by the JTS or by the OS. | Daily | OS | Timesheets - monthly Monthly rep. – monthly Interim reports - six-monthly |
| 1a | JTS – partner country OS. The partner country OS is a partner in the consortium that implements the TASC and is responsible to the OS that is the contractor for the TASC for the eligibility of costs incurred under the TASC in the partner country (subject to the provisions of the partnership agreement that should be concluded between the two OSs; where the partner country operates in indirect management, the control of costs incurred in the partner country may be delegated to its CFCU which would be referred to as “the control body”). In fact this line communication is analogous to the one bearing the no 1: when costs are incurred in the partner country, approval should be obtained from the partner country OS first. However, this can be agreed differently by the OSs for each programme. | Daily | OS | Timesheets - monthly Monthly rep. - monthly |
| 2 | JTS – DEU. Although the OS is the contractor for the TASC, the JTS will be mainly implementing it. The DEU is the CA for the TASC and it might occur that it contacts the JTS directly for some issues; direct contact should increase the efficiency of communication and decrease the possibilities for misinterpretation. By default, the communication will be directed from the DEU to the JTS (but the JTS should always address the OS first, which will address the DEU if needed) | Monthly | DEU | n/a |
| 2a | JTS – partner country DEU. Since the partner country DEU bears no responsibility for the implementation of the TASC, the communication should be minimal, if any. If information on the TASC is needed, the DEU that is the CA for the TASC should be contacted (see line of communication no 5). If contacted directly, the JTS should always consult the OS and the DEU that is the CA for the TASC before replying. | Rarely | DEU | n/a |
| 3 | OS - DEU. The DEU is the CA for the TASC, whereas the OS is the contractor; thusly this relation is the most important for the efficient and effective implementation of the TASC. Subject to provisions of the ToR, some activities requiring funding out of the incidental expenditure of the TASC would have to be approved by the DEU before they are incurred while for others the opinion of the auditor –expenditure verification- will be taken into account. Consultations will take place frequently, especially at the beginning of the implementation of the TASC. | Weekly | DEU | Inception – one per contract Progress – every 6 months Draft final a month before the end – one per contract Final – one per contract |
| 4 | OS – partner country OS. Relations should be regulated in the partnership agreement concluded between the two OSs regarding the implementation of the TASC. Very important for the efficiency, effectiveness and regularity of implementation of the TASC. Some communication might be directed through the JTS; if not, the JTS should be copied/informed whenever appropriate. | Weekly | OS | JTS reports - monthly |
| 4a | Partner country OS – partner country DEU. This relation does not affect the implementation of the TASC in any way. | n/a | n/a | n/a |
| 5 | DEU – partner country DEU. Consultations mainly when preparing the ToR or approving the reports under the TASC. Partner country DEU will be interested in the objectives of the TASC when creating the ToR and might be able to confirm some data from the reports when they are submitted. | 6-monthly | DEU that is the CA for the TASC | n/a |
| 6 | JMC – other bodies. JMC is generally not interested in details regarding the implementation of TASC, as long as there are no problems affecting the implementation of the CBC programme. The JMC is in charge of approving the JTS annual work plan as well as the communication and visibility plan of the programme. Both OSs and both DEUs are represented in the JMC and will be informed on the implementation of the TASC because of the lines of communication 1 to 5 described above. | 6-monthly | Partner country OS (chairs the JMC) | Annual report on implementation - yearly |

Table 2: Category II (programme related) relations between programme bodies under direct management

| Line of comm. | Description | Anticipated frequency of comm. | Body with “higher authority” | Reporting provisions (type - frequency) |
| --- | --- | --- | --- | --- |
| 1 | JTS - OS. By default, all JTS activities related to day-to-day implementation of the CBC programme require prior approval or at least examination by the OS (refer to the JTS manual for precise instructions for each task in Sections C-E). Exceptions are made only for tasks related to the JTS’s assistance to the CA in the evaluation of calls for proposals (if such assistance is required from the CA) and in matters related to monitoring of projects under implementation by the JTS (in which case the OS should be informed on monitoring plans and outcomes of the monitoring visits). | Daily | OS | Timesheets – monthly Annual reports on implementation - yearly |
| 1a | JTS – partner country OS. Analogous relations as in the line of communication no 1: partner country OS is genuinely interested in the efficiency and effectiveness of programme implementation and should always be consulted for any programme related matters. Depending on the specific task, this can be done either directly by the JTS, or the OS can consult the partner country OS before passing the information further to the DEU (for details refer to relevant sections of the JTS manual). | Daily | Partner country OS | Timesheets – monthly Annual reports on implementation - yearly |
| 2 | JTS – DEU. Since the JTS is also set up to assist the DEU in matters related to the implementation of the programme, this relation is very important. Although most communication will go through the OS, there are some tasks that might require direct communication, e.g. where this will increase the efficiency of communication (e.g. capacity building for grant beneficiaries and potential applicants, monitoring of implemented projects, information campaigns, etc.), or where this is necessary because of the rules applicable (e.g. confidentiality during the evaluation of project proposals where the CA may require the JTS’s support according to the framework agreement). | Monthly | DEU | Summary monitoring visit report – 6 monthly |
| 2a | JTS – partner country DEU. The partner country is not the CA and has no jurisdiction over either the implementation of CBC projects or the TASC, but is genuinely interested in the success of the programme and might send queries to the JTS to this regard. The DEU and the OS should always be copied or informed on the queries as well as on the replies and should be consulted before any reply is dispatched. | 6-monthly | Partner country DEU | Summary monitoring visit report (copy) – 6 monthly |
| 3 | OS - DEU. The most important relation under this set-up as it concerns every aspect of implementation of the programme. The DEU is the CA, while the OS is the main stakeholder of the programme. | Weekly | DEU | Annual reports on implementation - yearly |
| 4 | OS – partner country OS. All decisions related to the implementation of the programme must be made with consensus of these two parties – either formally through JMC decisions, or informally for other tasks. A good partnership needs to be established since both bodies are genuinely interested in the success of the programme. The partner country OS is always the chair of the JMC (see line of communication no 6) | Daily | OS | n/a |
| 4a | Partner country OS – partner country DEU. These two institutions are not in charge of contracting or monitoring projects under the programme, but are genuinely interested in the efficiency and effectiveness of the programme. This relation will be limited to consultations regarding various programme implementation issues to be communicated to the leader OS and the DEU. |  |  |  |
| 5 | DEU – partner country DEU. Communication will take place through the JMC or during bi-lateral coordination meetings of all programme bodies organised when strategic decisions need to be made. The DEU is solely responsible for finance and contracting issues in the entire programme territory and might consult or share relevant information with the partner country DEU, depending on their internal arrangement. | 6-monthly | DEU | n/a |
| 6 | JMC – other bodies. Most of the interaction takes place during the JMC meetings (at least twice a year) or through written procedure (ad hoc, when needed). All other bodies are represented in the JMC and will always be informed this way. JMC meetings should be organised whenever the JMC needs to make strategic decisions such as how each call for proposals should look like, provision of advisory opinion on the list of operations selected, approval of the annual report on implementation or revision of the programme document. Technical matters such as examination and approval of the communication and visibility plan, approval of the evaluation plan or approval of the JTS annual work plan can be made using written procedure. | 6-monthly | JMC | Annual report on implementation - yearly |

B	Indirect Management

The relations among bodies responsible for implementation of a cross-border programme under indirect management is presented in Graph 2.

JTS

Antenna

CA for the TASC

Country B

Strategic decisions

Partner in the TASC

Day-to-day implementation of the TASC

Country A

(where the CA is located)

Interested in success of the programme. Member of the TASC SC

HOS

Contractor for the TASC

DEU

DEU

OS

JMC Chair

1b

3

4b

3a

1

4c

6

5

7

CBC Body

CFCU

CA for grants

1a

2

4a

4

JMC

Graph 2: Organisational structure of programme bodies in indirect management

The left-hand side of the graph presents the structures in country A, where the CA is located, whereas on the right-hand side the programme structures in country B – the partner country – are presented.

The programme bodies are presented by rounded rectangles in different colours, depending on the type of the body; programme bodies in country B are displayed in a lighter colour, because their responsibility for programme implementation under IPA II is somehow less significant than that of the programme bodies in the country A where the CA is located. The major role of each body is briefly described in the respective callouts. Please note that in country A, the OS has 2 very important bodies that are independent from each other – the CBC Body and CFCU; however, both these bodies are under the jurisdiction of the Head of Operating Structure (HOS), represented by the HOS office.

Connections between the bodies present possible lines of communication between them. Arrows indicate possible directions of communication; note that all communications are bi-directional. Lines of communications in country B are dashed because of their relative significance. Each line of communication is labelled with a number. These numbers are used as references when describing the communications in the text and tables below.

Please note that the JMC is presented by a large transparent rounded rectangle with dashed outline that represents the communication line with other programme bodies (line no 6). This rectangle representing the JMC overlaps partially with all other bodies since all bodies have their representatives in the JMC. There is no individual communication line between any of the bodies with the JMC, as the communication is done through either official JMC meetings where all bodies are present, or written procedure that always includes all bodies.

Table 1: Category I (TASC related) relations between programme bodies under indirect management

| Line of comm. | Description | Anticipated frequency of comm. | Body with “higher authority” | Reporting provisions (type - frequency) |
| --- | --- | --- | --- | --- |
| 1 | JTS – CBC Body. The CBC Body is the contractor for the TASC which is used for financing operations of the JTS; therefore each activity carried out by the JTS by default requires the prior approval by the CBC Body, especially when the activity involve incidental costs. Communication goes both ways since tasks can be initiated either by the JTS or by the CBC Body. | Daily | OS | Timesheets - monthly Monthly rep. - monthly |
| 1a | JTS – CFCU. The CFCU has no jurisdiction over the implementation of the TASC, but is one of its beneficiaries. Since the CFCU is the CA for projects awarded under the programme, it can request the realisation of activities by a cost implication under the budget of the TASC (e.g. ad hoc on-the-spot checks, organisation of events, meetings, etc.). Whenever any such request is sent by the CFCU to the JTS, the CBC Body should always be informed/copied; if costs are to be incurred, prior approval by the CBC Body is required. In all cases issues of confidentiality have to be taken into account (e.g. when the evaluation of project proposals is under way). | Weekly | CFCU | n/a (reporting requirements are covered under line of communication no 1) |
| 1b | JTS – partner country OS. The partner country OS is a partner in the consortium that implements the TASC and is responsible to the CBC Body that is the contractor under the TASC regarding the eligibility of costs incurred in the partner country (subject to the provisions of the partnership agreement that should be concluded between the two OSs; where the partner country operates in indirect management, the control of costs incurred in the partner country can be delegated to its CFCU that can in this case be referred to as the “Control Body”). The line of communication is analogous to the one described under no 1: when costs are incurred in the partner country, approval should be obtained from the partner country OS first. This can be agreed differently by the OSs for each programme. | Daily | OS | Timesheets - monthly Monthly rep. - monthly |
| 2 | CBC Body – CFCU. As explained under relation 1a (above) this relation is determined by the characteristics of the TASC. Whenever the CFCU has requests that cause costs to be incurred under the TASC, the CBC Body needs to approve the request. Close communication will take place, but will in most cases go through the JTS that is the primary beneficiary of the TASC. The HOS office might be involved on a case-by-case basis if appropriate, as it has jurisdiction over both bodies. | Weekly | CBC Body | n/a (reporting requirements are covered under relation No 1) |
| 3 | JTS – DEU. Although the CBC Body is the contractor for the TASC, the JTS will be mainly implementing it. The DEU is the CA for the TASC and it might occur that it contacts the JTS directly for some issues; direct contact should increase the efficiency of communication and decrease possibilities for misinterpretation. By default, communication will be directed from the DEU to the JTS (the JTS should always address the OS first, which will address the DEU if needed). | Monthly | DEU | n/a |
| 3a | JTS – partner country DEU. Since the partner country DEU bears no responsibility for the implementation of the TASC, the communication should be minimal, if any. If information on the TASC implementation is needed, the DEU that is the CA for the TASC should be contacted by the partner country DEU (see line of communication no 6). If the DEU in the partner country directly contacts the JTS, the latter should always consult with the OS and the DEU that is the CA for TASC before replying. | Rarely | DEU | n/a |
| 4 | CBC Body – DEU. The DEU is the CA for the TASC, whereas the CBC Body is the contractor; thusly this relation is the most important for the efficiency of implementation of the TASC. Subject to provisions of the ToR, before incurring some expenses under incidental expenditure, the contractor might require prior approval by the DEU, while for others the opinion of the auditor –expenditure verification- will be taken into account. Consultations will take place frequently, especially at the beginning of the implementation of the TASC. | Weekly | EUD | Inception – once per TASC contract Progress – 6 months Final – once per TASC contract |
| 4a | CFCU – DEU. This relation has no significance in terms of the implementation of TASC. | Never | n/a | n/a |
| 4b | HOS – DEU. This relation has no significance in terms of the implementation of TASC. | Never | n/a | n/a |
| 4c | Partner country OS – partner country DEU. This relation does not affect the implementation of TASC in any way. |  |  |  |
| 5 | CBC Body – partner country OS. Relations should be regulated in the partnership agreement concluded between these two bodies regarding the implementation of the TASC. Very important for efficiency, effectiveness and regularity of the TASC implementation. Some communication might be directed through the JTS, if not the JTS should be copied/informed as appropriate. | Weekly | OS | JTS reports - monthly |
| 6 | DEU – partner country DEU. Consultations mainly when preparing the ToR or approving the reports for the TASC. The partner country DEU will be interested in the objectives of TASC when creating the ToR and might be able to confirm some data from the reports when they are submitted. | 6-monthly | DEU that is the CA for TASC | n/a |
| 7 | JMC – other bodies. The JMC is generally not interested in details regarding the implementation of the TASC, as long as there are no problems affecting the implementation of the programme. The JMC is in charge of approving the JTS annual work plan as well as the communication and visibility plan of the programme. Both OSs and both DEUs are represented in the JMC and will be informed on the implementation of the TASC because of the lines of communication 1 to 5 described above. | 6-monthly | Partner country OS (chairs the JMC) | Annual report on implementation - yearly |

Table 2: Category II (programme related) relations between programme bodies under indirect management

| Line of comm. | Description | Anticipated frequency of comm. | Body with “higher authority” | Reporting provisions (type - frequency) |
| --- | --- | --- | --- | --- |
| 1 | JTS – CBC Body. By default, all JTS activities related to day-to-day implementation of the CBC programme require prior approval or at least examination by the CBC Body (please refer to the Sections C-E of the JTS manual for precise instructions on each task). Exceptions are made only for tasks related to the JTS’s assistance to the CFCU in the evaluation of calls for proposals (if such assistance is required by the CFCU) and in matters related to monitoring of projects under implementation by the JTS (in which case the CBC Body should be informed on monitoring plans and outcomes of monitoring visits). | Daily | OS | Timesheets – monthly Annual reports on implementation – yearly Summary monitoring visit reports – 6 monthly |
| 1a | JTS – CFCU. Since the CFCU is the CA for all programme priority measures except the TA priority, and the JTS is set up to assist the programme bodies in matters related to the implementation of the programme, this relation is very important. The vast majority of tasks in sections C-E of the JTS manual require the approval by the programme’s CA. | Daily | CFCU | Monitoring visit reports – 6 monthly Annual reports on implementation - yearly |
| 1b | JTS – partner country OS. This is analogous to the line of communication no 1: the partner country OS is genuinely interested in the efficiency and effectiveness of programme implementation and should always be consulted for any programme related matter. Depending on the specific task, this can be done either directly by the JTS, or the CBC Body can consult the partner country OS before passing the information further to the CA or the DEU (for details refer to the relevant sections of the JTS manual). | Daily | Partner country OS | Timesheets – monthly Annual reports on implementation - yearly |
| 2 | CBC Body – CFCU. The most important relation under this set-up, since these two bodies are parts of the same structure – the Operating Structure of the country where the CA is located. Relations between these two bodies will most directly affect the efficiency and effectiveness of the programme. Communication is made directly, or through the JTS, or through the JMC and concerns literally every aspect of programme implementation since all tasks described in the JTS manual require examination/approval by both bodies. | Daily | CFCU | Annual report on implementation - yearly |
| 3 | JTS – DEU. The DEU is not the contracting authority under indirect management and therefore this relation is not very significant. Direct communication shall take place only in exceptional cases and with copy to the CBC Body. | Rarely | DEU | n/a |
| 3a | JTS – partner country DEU. The partner country DEU is not the contracting authority under indirect management and therefore this relation is not very significant. Direct communication shall take place only in exceptional cases and with copy to the CBC Body. | Rarely | Partner country DEU | n/a |
| 4 | CBC Body – DEU. Although the DEU is not the CA under indirect management, many decisions related to the implementation of the programme require the ex-ante control by the DEU. These approvals are chiefly related to the line of communication no 4a (CFCU - DEU) but as the CBC Body needs to check many tasks described in the Sections C-E of the JTS manual, direct consultations are expected to take place. | Monthly | DEU | Annual reports on implementation - yearly |
| 4a | CFCU – DEU. The DEU may exercise ex-ante controls on the tendering of contracts, launch of calls for proposals and the award of contracts and grants for the following stages of procurement and grant award: - Approval of contract notices for procurement, work programmes for calls for proposals and any corrigenda thereof; - Approval of tender dossiers and guidelines for applicants; - Approval of the composition of evaluation committees; - Approval of evaluation reports and award decisions; - Approval of contract dossiers and contract addenda. The DEU may decide to perform ex-post controls, including audits and on-the-spot checks, at any time on any contract or grant awarded by the CFCU. The DEU may authorise a person or an entity to perform ex-post controls on its behalf. This will be done in direct communication between these two bodies. This approval circuit is not reflected in the tables of the JTS manual since it does not involve the JTS directly, but the JTS should be aware that this additional approval circuit shall increase the length of planned deadlines. | Weekly | DEU | Annual reports on implementation - yearly Annual reports on the implementation of IPA II assistance under indirect management submitted by the NIPAC - yearly Annual financial report – yearly |
| 4b | OS – DEU. As described under the line of communication no 4 and 4a, most interaction between the OS and the DEU will go through the CFCU. However, some consultations can be done directly between the HOS Office and the DEU; in these cases the CFCU and the CBC Body should be always informed/copied. | Monthly | DEU | n/a |
| 4c | Partner country OS – partner country DEU. These two institutions are not in charge of contracting or monitoring the implementation of projects under the programme, but are genuinely interested in the efficiency and effectiveness of the programme. Their communication will be limited to consultations regarding various programme implementation issues, shared with the CBC Body and the CA of the programme. | Monthly | DEU | n/a |
| 5 | OS – partner country OS. All decisions related to the implementation of the programme must be made by consensus of these two parties – either formally through JMC decisions, or informally for other tasks. A good partnership needs to be established since both bodies are genuinely interested in the success of the programme. Mostly, communication will be between the CBC Body and its counterpart in the partner country (if the partner country has received entrustment of budget implementation tasks, the CBC Body of the partner country will be the counterpart; otherwise, it will be the OS). The partner country OS always holds the chair of the JMC (see 7 below). | Daily | OS | n/a |
| 6 | DEU – partner country DEU. Communication will take place through the JMC or during bi-lateral coordination meetings of all programme bodies that will take place when strategic decisions need to be made. The partner country DEU, unlike the DEU, has no role in the ex-ante and ex-post controls (see 4a above). However, in the spirit of good partnership, the partner country DEU’s opinion should be taken into account for important decisions. | 6-monthly | DEU | n/a |
| 7 | JMC – other bodies. Most instances of communication take place during JMC meetings (at least twice a year) or through written procedure (ad hoc, when needed). All other bodies are represented in the JMC and will always be informed this way. JMC meetings should be organised whenever JMC needs to make strategic decisions, such as how each call for proposals should look like, provision of advisory opinion on the list of operations selected, approval of the annual report on implementation or revision of the programme document. Technical matters such as examination and approval of the communication and visibility plan or approval of the JTS annual work plan can be made using written procedure. | 6-monthly | JMC | Annual report on implementation - yearly |

In general, one technical assistance service contract (TASC) covers one CBC programme. However, there are two cases where TA funds from two programmes were merged into one single TASC: 1) in Montenegro, a single TASC is covering the TA priorities of Montenegro-Albania and Montenegro-Kosovo cross-border programmes and 2) in Serbia, a single TASC is covering the TA priorities of Serbia-Bosnia and Herzegovina and Serbia-Montenegro cross-border programmes.

Article 76 of the Framework Agreement concluded between the European Commission (EC) and the beneficiary country.

In indirect management the CFCU is responsible for contracting of funds available for the programme, with the exception of the allocation for the TA priority, for whose contracting the relevant DEU is always responsible.