## Sheet1
| Action Package for CBC Performance Framework | Last Draft: 06.04.2017
No | Components / Aims | Evaluat. Recom. | Action by: | Action by CBIB+2 |  |  |  | Timing**
[5 empty] | S/T | M/T | L/T | Indicative action period
A. Better focused programmes
A.1 | IPA II & III programmes have more feasible objectives and outcomes | R6 | A.1a. DG NEAR should issue guidance on programme review |  |  |  |  | DG NEAR guidance by Autumn 2017 and lessons learnt for IPA III CBC programming
A.2 | Rework/sharpen up performance frameworks in IPA II programme review | R37 | A.2a. OSs conduct or commission programme reviews | A.2b. Programme-specific advice or training sessions on the review |  |  |  | 2018
A.3 | Strengthen the availability/quality of local and regional statistics | R7 | A.3a. Coordinated action between OSs and Statistical Offices | A.3b Specific advisory role - preparation of ToR for hiring statistical experts under TASCs |  |  |  | 2018-2020
B. Better focused CfP
B.1 | Publish a workplan or forecast of CfP for the rest of IPA II period | R17 & R29 | B.1a. CAs to develop and publish the workplan |  |  |  |  | By Summer 2017
B.2 | Focused scope of CfP: fewer SOs, one-theme CfP, etc | R9 & R28 | B.2-6a. CAs/OSs/JTSs participation in B.2-6c | B.2-6b. Specific advice and/or design of training packages on B.5 and B.6 , including good practice B.2-6c. Programme-specifc advice and/or training sessions on B.5 and B.6 with CAs/OSs/JTSs/assessors prior to the publication of a CfP |  |  |  | B.2-6b. By Summer 2017 B.2-6c. On-going
B.3 | Greater weight of the CBC dimension when evaluating applications | R10 & R11
B.4 | Raised minimum grant size while keeping an allocation for small-scale operations or alternatively introduce financial support to third parties | R12
B.5 | Clear performance framework & assessors guidance | R30 & R31
B.6 | Improved applicants' performance framework (focus on logframe & indicators) | R32
C. More realistic and robust system of indicators
C.1 | Supplement and systematise indicators in IPA II CBC programmes | R37 |  | *C.1b. Finalise a proposed list of supplementary & common indicators for all IPA II CBC programmes |  |  |  | Mar-Apr 2017
C.2 | Use the improved system of indicators in IPA II CBC programmes |  | C.2a. CAs/OSs/JTSs to introduce the improved indicators system | C.2b. Pilot for the MK-AL programme, then roll out |  |  |  | Pilot Nov 2016-May 2017, Roll out from Jun 2017
C.3 | Apply lessons learnt when preparing IPA III CBC programmes |  | C.3a. OSs embed lessons learnt when programming IPA III CBC |  |  |  |  | 2020-2021
D. Data management, collection, analysis & reporting
D.1 | Data collection on indicators from grant beneficiaries or contractors (strategic projects) | R33 | D.1a Continuous data collection by JTSs from grant beneficiaries and contractors during (and even after) their project implementation | D.1b. Training events on logframe/indicators for applicants invited to submit full applications or specific advice to the partners prior to the contract signature (initially by CBIB+, then by JTSs) |  |  |  | D.1a. Regular collection of data (on a 6-monthly basis & more frequently) as part of the JTS monitoring role D.1b. In each CfP
D.2 | Management of collected data | R34 | D.2a Development and operation of a monitoring system (MS) by CAs/OSs/JTSs | D.2b. Develop a guide for the MS and offer training for its use and operation, as well as advisory support. |  |  |  | D.2b. Set up the monitoring system by end of 2017 for every programme and deliver the necessary capacity building. Then autonomous running.
D.3 | Data analyses and regular reporting, including annual implementation reports (AIRs) and publication on programme performance on the dedicated websites | R35 & R37 | D.3a. Use data analyses for formal (e.g. AIR) and informal (e.g. on programme website) reporting by OSs/JTSs | D.3b* Develop and offer a programme-level reporting template and develop a WB CBC level template |  |  |  | D.3b. Mar-May 2017 for the template AIR at programme level and for the template at WB CBC level in summer 2017
D.4 | Carry out CBC performance analyses, overviews, etc. at WB-level. | R36 | D.4a DG NEAR should request and/or endorse it. | D.4b. OSs carry out analyses with the assistance of the JTSs and provide overviews and comparisons. CBIB+ can have an advisory role in designing, performing, analysisng and reporting. |  |  |  | Published on websites at least once a year
Annually from the beginning of 2018
E. Surveys - see Summary Table
E.1 | Obtain feedback from successful and unsuccessful applicants | R33 | E.1a. OSs/JTSs to conduct ex-post surveys with the support of CBIB+2 | E.1b. Prepare ex-post surveys and analyse their responses for all future IPA II CfP via OSs/JTSs (several launched for IPA via OSs/JTSs) |  |  |  | On-going
E.2 | Obtain feedback from potential beneficiaries / local population | R22 & R23 | E.2a. OS/JTS to conduct info events surveys with the support of CBIB+2 | E.2b. Prepare surveys to be conducted at info events by OSs/JTSs (MK-AL, AL-XK, XK-MK launched*, others to follow) and analyse their responses |  |  |  | On-going
E.3 | Obtain feedback from JMC members | R34 | E.3a. OS/JTS to conduct surveys of JMCs with the support of CBIB+2 | E.3b. Prepare surveys for JMC members, via OS/JTS (AL-XK and MK-AL launched* via OS/JTS, others to follow) and analyse their responses |  |  |  | On-going
E.4 | Draw lessons from the above and share with all the main CBC actors | R40 |  | E.4b. Analyse the results of the above surveys and disseminate the findings |  |  |  | On-going
F. Programme evaluations
F.1 | To be performed during the lifetime of IPA II | R38 | F.1a. DG NEAR should issue an instruction on evaluations of programmes implemented under direct management | F.1b. Advisory support or training for all programmes |  |  |  | By Autumn 2017
|  |  | F.1aa. OSs to commission evaluations under the TASCs for programmes implemented under indirect management |  |  |  |  | 2018 - 2019
2018 - 2019
G. Developing a performance culture
G.1 | Sharing and learning from experience (all main CBC actors incl. JMCs) | R40 | G.1a. Published on programme websites by CAs/OSs/JTSs | G.1b. Yellow & Blue, monthly flash news, Best Practice Database, CBIB+2 website, etc* |  |  |  | On-going
G.2 | Set up and steer a technical working group (TWG) on 'Impact Assessment & Monitoring' |  |  | G.2b. Invite nominations, convene meeting(s), steer discussions, provision of technical inputs (analysis), etc. |  |  |  | From June 2017
G.3 | Use the Regional CBC Forum |  |  | G.3b. Plan sessions on impact assessment & monitorring in the 5th & 6th CBC Forums |  |  |  | Autumn 2017 & Summer 2018 (tbc)
| *Completed or ongoing | ** | Short-term (S/T): Immediately relevant to the implementation of IPA II CBC
Medium-term (M/T): Particularly relevant to mid-term IPA II CBC programme review
Long-term (L/T): Particularly relevant to IPA III CBC programming