## General Overview
PROPOSAL OF A MONITORING TEMPLATE | [6 empty] | Formula to calculate Project Quality
MONITORING VISIT REPORT | [6 empty] | 78.125 | 1 | >75% = High Quality
Project Information | [7 empty] | 0 | <=50% and >=75% = Medium Quality
Contract title: | [7 empty] | 0 | >50% and >=25% = Low Quality
Coordinator: | [7 empty] | 0
Co-beneficiaries:
Contract number:
Project duration:
Implementation start date:
Progress or interim report(s) received (dates):
Project monitoring visits (date, venue and month of implementation):
Project's performance level: | 100 | / | 128 | High quality
Circulation Sheet
Step | Name and Surname |  |  |  | Submission Date | Signature
JTS TM in charge
Head of JTS (to endorse)
Programme Managers at OSs (for information)
Contracting Authorities TMs (for information)
Overview of the monitoring visit
Feedback from the grant beneficiary
Comments:
Signature ________________ _____ Date: __________________

## Checklist
| Question number | Specific question to be addressed | Comments | Overall performance | Recommendations |  |  |  |  | Serious deficiencies
|  |  | There are deficiencies which are so serious that, if not addressed, they can lead to failure of the action. Major adjustments and revision of the project strategy are necessary. | Serious deficiencies | [5 empty] | Improvements needed
|  |  | There are issues which need to be addressed; otherwise the global performance of the action may be negatively affected. Improvements are necessary, even if major revisions of the action’s strategy are not required. | Improvement needed | [5 empty] | Satisfactory
|  |  | The situation is considered satisfactory, but there is room for improvements. Recommendations are useful, but not vital for the action. | Satisfactory | [5 empty] | Very good
|  |  | The situation is considered highly satisfactory, largely above average and potentially a reference for good practice. Recommendations focus on the need to adopt these good practices in other actions. | Very good | [5 empty] | Not applicable
Not applicable
1. RELEVANCE
| 1.1 | Are the objectives of the intervention still responding to target groups’ needs/priorities as at the moment of submitting the project? |  | Improvements needed |  | 0 | 0 | 2 | 0 | 0
| 1.2 | Is the level of project relevance according to other elements (e.g. policy factors, institutional set-up, etc.) still significant? |  | Very good |  | 0 | 0 | 0 | 0 | 4
|  |  | ASSESSMENT | Satisfactory |  | 0 | 0 | 2 | 0 | 4 | 6 | 8 | 0.75
2. DESIGN
| 2.1 | Is the project well designed, with activities' complexity, duration and timing well defined, balanced and commensurate to beneficiaries' capacity? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 2.2 | Is the project logic well defined and reflected in a good logframe, with objective verifiable indicators (OVIs), and adequate targets? |  | Very good |  | 0 | 0 | 0 | 0 | 4
| 2.3 | Are OVIs realistic and likely to be achieved and are measurable? |  | Improvements needed |  | 0 | 0 | 2 | 0 | 0
| 2.4 | Has the project appropriate support by the local/regional stakeholders (local field situation)? |  | Very good |  | 0 | 0 | 0 | 0 | 4
| 2.5 | Are the risk analysis/ preconditions/ assumptions of the project comprehensive and relevant? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
|  |  | ASSESSMENT | Satisfactory |  | 0 | 0 | 2 | 6 | 8 | 16 | 20 | 0.8
3. EFFICIENCY
| 3.1 | Are the activities being implemented in line with the description of the action, including the timetable of activities/action plan? Should there be any adjustments needed? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 3.2 | Are activities being implemented within the budget envisaged? |  | Very good |  | 0 | 0 | 0 | 0 | 4
| 3.3 | Were all partners adequately involved in the realization of the action? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 3.4 | Where applicable, were cross-border partners adequately involved/consulted in the realization of the action? |  | Improvements needed |  | 0 | 0 | 2 | 0 | 0
| 3.5 | If there have been changes in the timetable of activities or action plan, do the changes seem reasonable? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 3.6 | How well these changes have been managed? |  | Very good |  | 0 | 0 | 0 | 0 | 4
| 3.7 | Is it likely that all activities will be completed by the end of the period of implementation? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 3.8 | Have the staff involved in the project sufficient capacity (both in terms of quantity and quality) to manage the project? |  | Improvements needed |  | 0 | 0 | 2 | 0 | 0
| 3.9 | Do the beneficiaries have a logical, consistent, regular and reliable system for monitoring project activities and outputs? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 3.10 | Is the project management making active use of the logframe and/or of other project management tools? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 3.11 | Are the outputs of the project delivered as planned (quantity/quality)? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 3.12 | Have the outputs been made available to the target group? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
|  |  | ASSESSMENT | Satisfactory |  | 0 | 0 | 4 | 24 | 8 | 36 | 48 | 0.75
4. EFFECTIVENESS
| 4.1 | Are the outcomes of the project being achieved as expected? Is there any evidence of this? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 4.2 | How are target groups assessing the quality and usefulness of the outcomes? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 4.3 | As presently implemented, what is the likelihood that the project purpose will be achieved? |  | Very good |  | 0 | 0 | 0 | 0 | 4
| 4.4 | Is the progress on achievement of project indicators satisfactory up to date? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
|  |  | ASSESSMENT | Satisfactory |  | 0 | 0 | 0 | 9 | 4 | 13 | 16 | 0.8125
5. IMPACT & CROSS-BORDER EFFECT
| 5.1 | Does it appear likely that the attainment of the project purpose will have an impact on the overall objective of the action? |  | Improvements needed |  | 0 | 0 | 2 | 0 | 0
| 5.2 | Will the project contribute to the Programme indicators? |  | Very good |  | 0 | 0 | 0 | 0 | 4
| 5.3 | To what extent does/will the operation have any indirect (positive/negative) impact? |  | Improvements needed |  | 0 | 0 | 2 | 0 | 0
| 5.4 | Is the project planned as: (a) a genuine joint project, (b) a mirror - same group of activities on each side of the border, or (c) a formalistic partnership - different types of activities with minor CB effect? |  | Very good |  | 0 | 0 | 0 | 0 | 4
| 5.5 | Are most of the activities jointly carried out with impact on both sides of the border? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 5.6 | Has the action a positive impact on the programme (e.g. any improvement at thematic sector level or local/regional CB area)? |  | Very good |  | 0 | 0 | 0 | 0 | 4
| 5.7 | Is the CBC programme recognized by the grant Beneficiaries as an opportunity for improving neighbourly relations? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 5.8 | Is the CBC programme recognized by the grant beneficiaries as a tool for improving the situation in a thematic sector (in line with Programme measures)? |  | Very good |  | 0 | 0 | 0 | 0 | 4
|  |  | ASSESSMENT | Satisfactory |  | 0 | 0 | 4 | 6 | 16 | 26 | 32 | 0.8125
6. SUSTAINABILITY
| 6.1 | How sustainable will be the transfer of project ownership (taking into account any hand-over strategy, the standing of the end recipient(-s) of project benefits/results, the experience within the project/related to project-content, staffing and other factors to be identified on a case by case basis)? |  | Not applicable |  | 4 | 0 | 0 | 0 | 0
| 6.2 | Will benefits/results of the project continue to be generated/used after its completion? |  | Not applicable |  | 4 | 0 | 0 | 0 | 0
| 6.3 | By whom, how and to what extent will further financing of benefits/results be ensured? |  | Satisfactory |  | 0 | 0 | 0 | 3 | 0
| 6.4 | Are there other additional elements fostering sustainability (e.g. policy aspects, institutional capacity, equal opportunities, social inclusion, environmental considerations, etc.)? |  | Not applicable |  | 4 | 0 | 0 | 0 | 0
| 6.5 | Where applicable, is the cross-border cooperation between the coordinator and co-beneficiaries likely to continue after the end of the project implementation? |  | Not applicable |  | 4 | 0 | 0 | 0 | 0
|  |  | ASSESSMENT | Satisfactory |  | 16 | 0 | 0 | 3 | 0 | 3 | 4 | 0.75
[7 empty] | Total: |  |  |  | 100 | 128

## Main Findings
1. Relevance |  |  |  | 6 | / | 8
2. Design |  |  |  | 16 | / | 20
3. Efficiency |  |  |  | 36 | / | 48
4 Effectiveness |  |  |  | 13 | / | 16
5 Impact & Cross-border Effect |  |  |  | 26 | / | 32
6 Sustainability |  |  |  | 3 | / | 4
Project visit total score: | 100 | / | 128
Key points/ findings:
Key points/ findings:
Key points/ findings:
Key points/ findings:
Key points/ findings:
Key points/ findings: