## Sheet1
Annex 09 - Timetable for Calls for Proposals - example template
Programme name:
Call publication number:
|  |  | 1st CfP | 2nd CfP | 2016 | [7 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019
| TASK | Days | Tentative start dates |  | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
| JMC Meeting | 1 | 2016-06-01 | bar: 2016 J; 2017 F; 2017 J; 2018 J; 2018 S; 2019 J; 2019 J
CALL | Publication of Call for proposal - C | 45 | 2016-09-16 | 2018-09-16 | bar: 2016 S; 2018 S
| Partner Search Forum |  | 2016-08-15 | 2018-08-15 | bar: 2016 A to 2016 S; 2018 A to 2018 S
| Organising info sessions |  | 2016-09-23 | 2018-09-23 | bar: 2016 S; 2018 S
EVALUATION | Step 1: Opening session & administrative check | 45 | 2016-10-31 | 2018-10-31 | bar: 2016 N; 2018 N
| Step 2: Assessment of concept notes | 90 | 2017-01-29 | 2019-01-29 | bar: 2016 N to 2017 J; 2018 N to 2019 J
| Step 3: Assessement of full applications | 45 | 2017-03-15 | 2019-03-15 | bar: 2017 M to 2017 A; 2019 M to 2019 A
| Step 4: Verification of eligibility | 60 | 2017-05-14 | 2019-05-14 | bar: 2017 M; 2019 M
| Final Approval Evaluation (OS, ECD, JMC) | 30 | 2017-06-13 | 2019-06-13 | bar: 2017 J; 2019 J
| Budgetary clearing & contracting | 60 | 2017-08-12 | 2019-08-12 | bar: 2017 J to 2017 A; 2019 J to 2019 A
MONITORING | Training for beneficiaries | 7 | 2017-08-19 | 2019-08-19 | bar: 2017 A; 2019 A
| Kick-off event |  | 2017-09-08 | 2019-09-08 | bar: 2017 S; 2019 S
| Monitoring GS Projects |  | Throughout | Throughout | bar: 2017 S to 2019 D
| Prepration of Annual Programme Implementation Report | 60 | 1 December each year | bar: 2016 D to 2017 J; 2017 D to 2018 J; 2018 D to 2019 J; 2019 D
Notes
It is proposed that the CfP launched in 2016 covers 2014 and 2015 IPA II allocations and the CfP lauched in 2018 covers 2016 and 2017 IPA II allocations
It is proposed that partner search forums will be held before the publication of the CfPs
It is proposed that all CfPs are restricted and not open
It is proposed that assessors will examine both concept notes and full applications
Formulas:
Tentative start dates = [Tentative start dates, row above]+C13
Tentative start dates = [Tentative start dates, row above]+20