## Budget
JTS Work Plan 2016-2018 - BUDGET |  |  |  | 2016 |  | 2017 |  | 2018 |  | ALL YEARS
Expenses | Description of cost | Total no. of units planned | Unit rate in Euro | # of units | Total cost | # of units | Total cost | # of units | Total cost | # of units | Total cost | Share
1. Fees (including overheads) |  |  |  |  | 102400 |  | 109600 |  | 90400 |  | 302400 | 59%
Key experts
Head of JTS | 1 person x 660 days | 660 days | 100 | 220 | 22000 | 220 | 22000 | 220 | 22000 | 660 | 66000
Non-key experts
JTS Task Manager | 1 person x 440 days | 440 days | 90 | 120 | 10800 | 160 | 14400 | 160 | 14400 | 440 | 39600
JTS Publicity and Information Officer | 1 person x 660 days | 660 days | 90 | 220 | 19800 | 220 | 19800 | 220 | 19800 | 660 | 59400
JTS Financial and Administrative Assistant | 1 person x 660 days | 660 days | 90 | 220 | 19800 | 220 | 19800 | 220 | 19800 | 660 | 59400
Assessors | 2 people x 30 days x 2 years x 2 countries | 240 days | 160 | 120 | 19200 | 120 | 19200 | 0 | 0 | 240 | 38400
Antenna
JTS Task Manager | 1 person x 440 days | 440 days | 90 | 120 | 10800 | 160 | 14400 | 160 | 14400 | 440 | 39600
2. Travel & subsistence costs |  |  |  |  | 21600 |  | 21600 |  | 21600 |  | 64800 | 12.64%
International travel costs | 1000 km a month x 3 years | 36000 km | 0.22 | 12000 | 2640 | 12000 | 2640 | 12000 | 2640 | 36000 | 7920
Local travel costs | 1500 km a month x 3 years | 54000 km | 0.22 | 18000 | 3960 | 18000 | 3960 | 18000 | 3960 | 54000 | 11880
Per diems abroad | 10 per diems x 3 years x 5 people | 150 per diems | 150 | 50 | 7500 | 50 | 7500 | 50 | 7500 | 150 | 22500
Per diems local | 15 per diems x 3 years x 5 people | 225 per diems | 100 | 75 | 7500 | 75 | 7500 | 75 | 7500 | 225 | 22500
3. Meetings & training |  |  |  |  | 17900 |  | 20900 |  | 6500 |  | 45300 | 8.839%
JMC meetings | 1 meeting x 3 years x 2 countries (lunch + venue for 30 participants per event) | 6 events | 1000 | 2 | 2000 | 2 | 2000 | 2 | 2000 | 6 | 6000
Info days | 3 days x 2 years x 2 countries | 12 days | 800 | 6 | 4800 | 6 | 4800 |  | 0 | 12 | 9600
Partner search forum | 1 event x 3 years | 3 events | 1000 | 1 | 1000 | 1 | 1000 | 1 | 1000 | 3 | 3000
Workshops for applicants | 3 events x 2 years x 2 countries (200 participants per event) | 12 events | 800 | 6 | 4800 | 6 | 4800 |  | 0 | 12 | 9600
Project clinics | 3 events x 2 years x 2 countries (100 participants per event) | 12 events | 800 | 6 | 4800 | 6 | 4800 |  | 0 | 12 | 9600
Workshops for grant beneficiaries | 3 events x 2 years x 2 countries (50 participants per event) | 12 events | 500 | 0 | 0 | 6 | 3000 | 6 | 3000 | 12 | 6000
Capacity building events for management structures | 1 event x 3 years (20 participants per event) | 3 events | 500 | 1 | 500 | 1 | 500 | 1 | 500 | 3 | 1500
4. Interpretation & translation |  |  |  |  | 4000 |  | 4000 |  | 4000 |  | 12000 | 2.341%
Interpretation | lump sum per year | 3 years | 2000 | 1 | 2000 | 1 | 2000 | 1 | 2000 | 3 | 6000
Translation | lump sum per year | 3 years | 2000 | 1 | 2000 | 1 | 2000 | 1 | 2000 | 3 | 6000
5. Evaluation & audit |  |  |  |  | 2000 |  | 44000 |  | 6000 |  | 52000 | 10.15%
Mid term evaluation (where appropriate) | per service | 1 service | 40000 |  | 0 | 1 | 40000 |  | 0 | 1 | 40000
Audit | per service (at least 6 reports) | 6 reports | 2000 | 1 | 2000 | 2 | 4000 | 3 | 6000 | 6 | 12000
6. Publicity & visibility |  |  |  |  | 14000 |  | 8000 |  | 14000 |  | 36000 | 7.024%
Promotional materials | lump sum per year | 3 years | 4000 | 1 | 4000 | 1 | 4000 | 1 | 4000 | 3 | 12000
Visibility Conference | 1 event x 2 countries (lunch/refreshment 250 participants) | 2 events | 6000 | 1 | 6000 |  | 0 | 1 | 6000 | 2 | 12000
Website | lump sum per year | 3 years | 4000 | 1 | 4000 | 1 | 4000 | 1 | 4000 | 3 | 12000
TOTAL |  |  |  |  | 161900 |  | 208100 |  | 142500 |  | 512500 | 100%

## Activities timeline
| 2016 | [11 empty] | 2017 | [11 empty] | 2018
Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Managing technical assistance
1.1… (insert individual activiities as indicated in JTS manual) |  |  |  | x | x | x | x
2. Calls for Proposals launching phase | [6 empty] | x | x | x
3. Calls for Proposals evaluation phase
4. Project monitoring etc
5. Programme monitoring
6. Publicity, visibility and information
7. Other
Note on B5: XS3: Enter x in respective cells. They will automatically become blue

## WLA summary - DM
Overview
Activity | 2016 | 2017 | 2018
I Management of technical assistance | 0 | 0 | 0
II Calls for proposals - launching phase | 0 | 0 | 0
III Calls for proposals - evaluation phase | 1 | 393 | 462
IV Project monitoring | 3 | 92 | 92
V Programme monitoring | 3 | 48 | 48
VI Publicity, visibility and information | 3 | 73 | 73
VII Other | 71 | 108 | 108
Total | 4 | 714 | 783
Number of staff required - No of days/215 (total number of work days in a year) | 0.018605 | 3.3209 | 3.6419
I Management of technical assistance
Activity | 2016 | 2017 | 2018
1. JTS work plan
2. Reports on TA activities performed & costs incurred under the service contract(s)
3. Initiate drafting requests for payment & for amendments to the budget
4. Ensuring visibility of outputs produced under TAGCs
5. Prior approval of costs associated with the work of JTS staff
6. Claims for the payment of salaries of the JTS staff & costs associated with their work
7. Preparing procurement documentation for supplies or services under TASCs
8. Assistance in procuring supplies and/or services under TASCs
9. Managing contracts for supplies or services under TASCs
10. Preparing & negotiating the application form (incl. budget) for the subsequent TASC and concluding the associated Grant/Service Contract
Total | 0 | 0 | 0
II Calls for proposals - launching phase
Activity | 2016 | 2017 | 2018
1. Work Programme
2. Call for Proposals Timetable
3. Partner Search Forums
4. Drafting calls for proposals and related documentation (application packs)
5. Publication/upload to the programme website
6. Information sessions
7. Workshops for potential applicants
8. Answering queries from interested applicants
9. Group consultation meetings with interested applicants
10. Individual consultation meetings with interested applicants
Total | 0 | 0 | 0
III Calls for proposals - evaluation phase
Activity | 2016 | 2017 | 2018
1. Drafting a proposal for the membership of the Joint Steering Committee/Evaluation Committee | 1 | 1 | 1
2. Arranging for hiring of assessors | 0 | 6 | 6
3. Proposal for assessors | 0 | 60 | 60
4. Receipt, registration and storage of proposals | 0 | 60 | 60
5a. Secretarial duties for the opening session, administrative check | 0 | 25 | 25
5b. Secretarial duties for the concept note evaluation | 0 | 100 | 100
5.c. Drafting letters notifying applicants on the status of their project | 0 | 50 | 50
5.d. Signing and dispatching letters notifying applicants | 0 | 50 | 50
6. Secretarial duties for the evaluation of full application forms | 0 | 0 | 50
7. Secretarial duties for the verification of eligibility, conclusions of the evaluation committee and production of the final evaluation report | 0 | 20 | 20
8. Drafting letters notifying applicants on the grant award or rejection of their project | 0 | 6 | 6
9. Signing and dispatching letters notifying applicants | 0 | 5 | 5
10. Budgetary clearing and contracting | 0 | 10 | 10
11. Publicising the award of grants | 0 | 0 | 12
12. Analysing statistical information on the Call for Proposals and measures for improving the quality of applications | 0 | 0 | 7
Total | 1 | 393 | 462
IV Project monitoring
Activity | 2016 | 2017 | 2018
1. Preparation of implementation package for project beneficiaries | 0 | 10 | 10
2. Implementation of seminars for project beneficiaries | 0 | 10 | 10
3. Opening and maintaining a file for each project | 3 | 15 | 15
4. Help line for project beneficiaries | 0 | 10 | 10
5. Advice on secondary procurement under grant contracts | 0 | 3 | 3
6. Early warning assessment of all projects and follow-up
7. Progress reports check and follow-up | 0 | 10 | 10
8. Developing an indicative monitoring visit schedule | 0 | 15 | 15
9. Conducting monitoring visits | 0 | 12 | 12
10. Drafting monitoring visit reports and follow-up | 0 | 1 | 1
11. Keeping relevant up-to-date project information in electronic form | 0 | 6 | 6
Total | 3 | 92 | 92
V Programme monitoring
Activity | 2016 | 2017 | 2018
1. Preparation of Annual and Final Implementation Reports | 0 | 10 | 10
2. Cooperating with external, independent evaluators during programme implementation | 0 | 10 | 10
3. Proposing amendments and revisions to the programming documents | 3 | 15 | 15
4. Performing the duties of the secretariat of the JMC | 0 | 10 | 10
5. Supply of information to partner countries' OSs for their reporting duties | 0 | 3 | 3
Total | 3 | 48 | 48
VI Publicity, visibility and information
Activity | 2016 | 2017 | 2018
1. Preparing, monitoring, evaluating and updating the Communication Action Plan (CAP) | 0 | 10 | 10
2. Maintenance of a programme website | 0 | 10 | 10
3. Organising information and publicity events | 3 | 15 | 15
4. Arranging printed materials and other manufactured or electronic media | 0 | 10 | 10
5. Ensuring programme visibility and compliance with visual identity rules | 0 | 3 | 3
6. Establishing and maintaining databases and supplying data | 0 | 10 | 10
7. Handling media inquires | 0 | 15 | 15
Total | 3 | 73 | 73
VII Other
Activity | 2016 | 2017 | 2018
1. Preparation of documentation for and oversight of joint operations identified outside calls for proposals | 5 | 20 | 20
2. Reporting irregularities | 30 | 40 | 40
3. Recording and reporting exceptions | 10 | 10 | 10
4. Filing – physical documentation | 10 | 20 | 20
5. Filing – electronic documentation | 10 | 10 | 10
6. Client enquiries that do not fall into any of the above mentioned tasks | 3 | 3 | 3
7. Facilitating any monitoring or audit missions related to the TAGCs | 3 | 3 | 3
8. Attending coordination meetings with the OS | 0 | 2 | 2
Total | 71 | 108 | 108
Note on C48: ob1: 100 projects from mid 2009, 1 day for every 4
Note on D48: ob1: 100 projects from mid 2009, 1 day for every 4

## WL calculation - DM
Annex 2c: Workload calculation for direct management mode (DM) For demostration and illustration purposes.
WORKLOAD CALCULATION FOR PROGRAMMES 2014-2020 OPERATING UNDER DIRECT MANAGEMENT
Total number of days required for operations of the JTS per year: |  |  |  | 884.225
Total number of working days available per year: |  |  |  | 215
Required number of staff to adequately perform all tasks listed below: |  |  |  | 4.1127
Activity I : Management of technical assistance | Applicable (y/n) | Variable | Value of the variable | Total days
1. JTS work plan | y |  |  | 3
2. Reports on TA activities performed & costs incurred under the service contract(s) | y |  |  | 66
2.1 Timesheets (2 hrs x No of staff = 1 day x 12 months) | y | Number of Staff | 2 | 6
2.2 Narrative reporting - inception, interim and final reports (preparation 5 + control 2 days =7 days per report) | y | Number of reports | 3 | 21
2.3 Financial reporting - inception and progress reports (preparation of the financial report - 1 day + control 1 day = 2 days; assistance and discussion with auditors 2 days) | y | Number of reports | 3 | 8
2.4 Preparation of monthly reports (3 days for preparing each montly report) | y | Number of monthly reports | 9 | 27
3. Initiate drafting requests for payment & for amendments to the budget (16 payment requests a month=1 day x 12 months=12 days; 2 notification letters x 2 days = 4 days) | y | No of payment requests | 16 | 16
4. Ensuring visibility of outputs produced under TAGCs (contact with media 0.5 days x 12 months=6 days; agreeing design of materials with subcontractors - 3 days; attending beneficiaries' visibility events: 10 projects x 2 days=20 days; updating programme website: 2 days x 12 months=24 days) | y | No of projects implemented | 10 | 53
5. Prior approval of costs associated with the work of JTS staff (No of JTS staff x 2 requests x 0.25 hrs x 12 months) | y | No of travels per staff per month | 2 | 1.5
6. Claims for the payment of salaries of the JTS staff & costs associated with their work (No of JTS staff x 2 requests x 0.5 hrs x 12 months) | y | No of travels per staff per month | 2 | 3
7. Preparing procurement documentation for supplies or services under TAGCs (No of tenders x 3 days) | y | No of tenders | 10 | 30
8. Assistance in procuring supplies and/or services under TAGCs (No of tenders x 0.5 days) | y | No of tenders | 10 | 5
9. Managing contracts for supplies or services under TAGCs (No of tenders x 1 day) | y | No of tenders | 10 | 10
10. Preparing & negotiating the application form (incl. budget) for the subsequent TAGC and concluding the associated Grant/Service Contract | y |  |  | 10
Total Activity I : Management of technical assistance |  |  |  | 197.5
Activity II : Calls for proposals - launching phase | Applicable (y/n) | Variable | Value of the variable | Total days
1. Work Programme | y |  |  | 0.5
2. Call for Proposals Timetable | y |  |  | 0.5
3. Partner Search Forums (2 PSFs for each CfP x 5 days = 10 days) applicable only if launch of a CfP is planned for that year | y | No of PSFs | 2 | 10
4. Drafting calls for proposals and related documentation (application packs) applicable only if launch of a CfP is planned for that year | y |  |  | 10
5. Publication/upload to the programme website - applicable only if launch of a CfP is planned for that year | y |  |  | 0.1
6. Information sessions (No of information sessions per country x 2 days (1 day travel and 1 day organisation) * No of JTS staff + 0,5 days preparing materials, 0,5 day reporting and filing) - Applicable only if launch of a CfP is planned for that year | y | No of sessions per country | 2 | 8.5
7. Workshops for potential applicants (No of workshops per country x 3 days - 1 day travel and 2 days organisation * No of JTS staff + 5 days preparing materials, 1 day reporting and filing) | y | No of workshops per country | 2 | 18
8. Answering queries from interested applicants (80 queries x 0.5 hrs = 5 days) - Applicable only if launch of a CfP is planned for that year | y | Average No of queries | 10 | 0.625
9. Group consultation meetings with interested applicants (1 day travel x 1 day meeting x No of JTS staff) | n | No of meetings | 5 | 0
10. Individual consultation meetings with interested applicants (2 hours preparation and 2 hours meeting x 1 JTS staff) | n | No of meetings | 20 | 0
Total Activity II : Calls for proposals - launching phase |  |  |  | 48.225
Activity III : Calls for proposals - evaluation phase | Applicable (y/n) | Variable | Value of the variable | Total days
1. Drafting a proposal for the membership of the Joint Steering Committee/Evaluation Committee | n |  |  | 0.5
2. Arranging for hiring of assessors (1 day for preparing ToR that is required in any case and 2 days for preparing tender dossier and implement the tender procedure) | n | 1=tender used 2=other option | 1 | 0
3. Proposal for assessors | n |  |  | 0.5
4. Receipt, registration and storage of proposals | n |  |  | 5
5a. Secretarial duties for the opening session, administrative check (1.5 hrs per proposal for opening and admin check (including requests for clarifications) in case of an open call, or 45 mins per proposal in case of a restricted call + 1 day arranging JSC mtgs + 3 days compiling the report + (3 days travel + 3 days participating at the mtgs)*3 JTS staff) | n | Estimated No of proposals received | 100 | 0
5b. Secretarial duties for the concept note evaluation (0.5 hrs per proposal for checking evaluation grids and summarising the scores + 1 day arranging JSC mtgs + 3 days compiling the report + (3 days travel + 3 days participating at the mtgs) | n | 1=restricted call 2=open call | 1 | 0
5.c. Drafting letters notifying applicants on the status of their project (No of projects received x 0.5 days per letter for drafting and cross-checking) | n | Estimated No of proposals received | 100 | 0
5.d. Signing and dispatching letters notifying applicants (No of projects approved x 0.2 days per letter for signing, dispatching and checking if received) | n | Estimated No of proposals received | 100 | 0
6. Secretarial duties for the evaluation of full application forms (0.75 hrs per proposal for checking evaluation grids and summarising the scores + 1 day arranging JSC mtgs + 3 days compiling the report + (3 days travel + 3 days participating at the mtgs) | n | Estimated No of projects recommended | 15 | 0
7. Secretarial duties for the verification of eligibility, conclusions of the evaluation committee and production of the final evaluation report (0.5 hrs per proposal for verification of eligibility; no additional time for mtgs and reports since this step should always be merged with other steps of the evaluation) | n | 1=merged with step 1 2=merged with step 2 | 1 | 0
8. Drafting letters notifying applicants on the grant award or rejection of their project (No of projects received x 0.5 days per letter for drafting and cross-checking) | n | Estimated No of full applications evaluated | 30 | 0
9. Signing and dispatching letters notifying applicants (No of projects approved x 0.2 days per letter for signing, dispatching and checking if received) | n | Estimated No of full applications evaluated | 30 | 0
10. Budgetary clearing and contracting (1 day per proposal for creating initial budget clearing table + 2 days per proposal for concultations with the CA and the beneficiary; this includes time needed for setting up a meeting, if necessary) | n | Estimated No of projects recommended | 15 | 0
11. Publicising the award of grants | n |  |  | 0.5
12. Analysing statistical information on the Call for Proposals and measures for improving the quality of applications | y |  |  | 5
Total Activity III: Calls for proposals - evaluation phase |  |  |  | 5
Activity IV : Project monitoring | Applicable (y/n) | Variable | Value of the variable | Total days
1. Preparation of implementation package for project beneficiaries | y | 1= first time 2=revision | 2 | 5
2. Implementation of seminars for project beneficiaries (No of implementation seminars x 3 days (1 day travel and 2 day organisation) * No of JTS staff + 5 days preparing materials, 1 day reporting and filing) | n | No of seminars | 1 | 0
3. Opening and maintaining a file for each project (average 2 days per project during the entire implementation period) | y | No of projects implemented | 10 | 20
4. Help line for project beneficiaries (No of projects * (2 days commenting reports + 3 days various consultations)) | y | No of projects implemented | 10 | 50
5. Advice on secondary procurement under grant contracts (No of projects * 10 tenders requiring consultations * 1 day) | y | No of projects implemented | 10 | 100
6. Early warning assessment of all projects and follow-up (No of projects * 2 days during the entire implementation period) | y | No of projects implemented | 10 | 20
7. Progress reports check and follow-up (No of projects * 2 days during the entire implementation period) | y | No of projects implemented | 10 | 20
8. Developing an indicative monitoring visit schedule | y |  |  | 0.5
9. Conducting monitoring visits (3 visits a year per project: 1 day travel + 1 day compliance check + 1 day interviews for ROM monitoring) | y | No of projects implemented | 10 | 90
10. Drafting monitoring visit reports and follow-up (1 day preparing reports + 1 day follow up per each visit) | y | No of projects implemented | 10 | 60
11. Keeping relevant up-to-date project information in electronic form (0.5 days a project per year) | y | No of projects implemented | 10 | 5
Total Activity IV : Project monitoring |  |  |  | 370.5
Activity V : Programme monitoring | Applicable (y/n) | Variable | Value of the variable | Total days
1. Preparation of Annual and Final Implementation Reports (3 days gathering information, 15 days preparing the report, 2 days preparing the annexes) | y |  |  | 20
2. Cooperating with external, independent evaluators during programme implementation | y |  |  | 2
3. Proposing amendments and revisions to the programming documents | y |  |  | 5
4. Performing the duties of the secretariat of the JMC (No of JMC meetings * (1 day preparing documents, 2 days * No of JTS staff travel and organisation of a meeting, 2 days preparing and finalising meeting minutes)) | y | No of JMC meetings | 2 | 14
5. Supply of information to partner countries' OSs for their reporting duties | y |  |  | 5
Total Activity V : Programme monitoring |  |  |  | 46
Activity VI : Publicity, visibility and information | Applicable (y/n) | Variable | Value of the variable | Total days
1. Preparing, monitoring, evaluating and updating the Communication Action Plan (CAP) | y |  |  | 5
2. Maintenance of a programme website (during 12 months, 0.2 days per post) | y | Average No of posts in a month | 10 | 24
3. Organising information and publicity events (No of events * (3 days preparation + 1 day reporting + No of JTS staff * 1 day travel and 1 day organisation) | y | No of events | 1 | 8
4. Arranging printed materials and other manufactured or electronic media (a lump-sum value of 5 days a year, negotiating design with the company selected) | y |  |  | 5
5. Ensuring programme visibility and compliance with visual identity rules (during 12 months, 2 days per month) | y |  |  | 24
6. Establishing and maintaining databases and supplying data (2 days * 12 months) | y |  |  | 24
7. Handling media inquires (0.5 days * 12 months) | y |  |  | 6
Total Activity VI : Publicity, visibility and information |  |  |  | 96
Activity VII : Other | Applicable (y/n) | Variable | Value of the variable | Total days
1. Preparation of documentation for and oversight of joint operations identified outside calls for proposals (per operation: 10 days preparation of documentation, 20 days oversight of operations, 5 days revising their reports, 5 days visibility activities) | y | p - preparation o - oversight r - reports v - visibility | porv | 40
2. Reporting irregularities | y |  |  | 5
3. Recording and reporting exceptions | y |  |  | 5
4. Filing – physical documentation | y |  |  | 12
5. Filing – electronic documentation | y |  |  | 12
6. Client enquiries that do not fall into any of the above mentioned tasks (visitors, potential applicants calling, potential interships negotiations, open days, offering advertisements, communication with EC in Brussels, communication with EUDs, OSs, etc) | y |  |  | 24
7. Facilitating any monitoring or audit missions related to the TAGCs | y |  |  | 5
8. Attending coordination meetings with the OS (all JTS staff attend meetings organised by the OS on regular basis - every 2 months: No of JTS staff x 1.5 days x 6 times a year) | y | No of staff | 2 | 18
|  |  | Total Activity VII : Other | 121

## WLA summary - IM
Overview
Activity | 2016 | 2017 | 2018
I Management of technical assistance | 0 | 0 | 0
II Calls for proposals - launching phase | 0 | 0 | 0
III Calls for proposals - evaluation phase | 0 | 0 | 0
IV Project monitoring | 3 | 92 | 92
V Programme monitoring | 3 | 48 | 48
VI Publicity, visibility and information | 3 | 73 | 73
VII Other | 71 | 108 | 108
Total | 3 | 321 | 321
Number of staff required - No of days/215 (total number of work days in a year) | 0.013953 | 1.493 | 1.493
I Management of technical assistance
Activity | 2016 | 2017 | 2018
1. JTS work plan
2. Reports on TA activities performed & costs incurred under the service contract(s)
3. Initiate drafting requests for payment & for amendments to the budget
4. Ensuring visibility of outputs produced under TAGCs
5. Prior approval of costs associated with the work of JTS staff
6. Claims for the payment of salaries of the JTS staff & costs associated with their work
7. Preparing procurement documentation for supplies or services under TASCs
8. Assistance in procuring supplies and/or services under TASCs
9. Managing contracts for supplies or services under TASCs
10. Preparing & negotiating the application form (incl. budget) for the subsequent TASC and concluding the associated Grant/Service Contract
Total | 0 | 0 | 0
II Calls for proposals - launching phase
Activity | 2016 | 2017 | 2018
1. Work Programme
2. Call for Proposals Timetable
3. Partner Search Forums
4. Drafting calls for proposals and related documentation (application packs)
5. Publication/upload to the programme website
6. Information sessions
7. Workshops for potential applicants
8. Answering queries from interested applicants
9. Group consultation meetings with interested applicants
10. Individual consultation meetings with interested applicants
Total | 0 | 0 | 0
III Calls for proposals - evaluation phase
Activity | 2016 | 2017 | 2018
1. Drafting a proposal for the membership of the Joint Steering Committee/Evaluation Committee | 0 | 0 | 0
2. Arranging for hiring of assessors | 0 | 0 | 0
3. Proposal for assessors | 0 | 0 | 0
4. Receipt, registration and storage of proposals | 0 | 0 | 0
5a. Secretarial duties for the opening session, administrative check | 0 | 0 | 0
5b. Secretarial duties for the concept note evaluation | 0 | 0 | 0
5.c. Drafting letters notifying applicants on the status of their project | 0 | 0 | 0
5.d. Signing and dispatching letters notifying applicants | 0 | 0 | 0
6. Secretarial duties for the evaluation of full application forms | 0 | 0 | 0
7. Secretarial duties for the verification of eligibility, conclusions of the evaluation committee and production of the final evaluation report | 0 | 0 | 0
8. Drafting letters notifying applicants on the grant award or rejection of their project | 0 | 0 | 0
9. Signing and dispatching letters notifying applicants | 0 | 0 | 0
10. Budgetary clearing and contracting | 0 | 0 | 0
11. Publicising the award of grants | 0 | 0 | 0
12. Analysing statistical information on the Call for Proposals and measures for improving the quality of applications | 0 | 0 | 0
Total | 0 | 0 | 0
IV Project monitoring
Activity | 2016 | 2017 | 2018
1. Preparation of implementation package for project beneficiaries | 0 | 10 | 10
2. Implementation of seminars for project beneficiaries | 0 | 10 | 10
3. Opening and maintaining a file for each project | 3 | 15 | 15
4. Help line for project beneficiaries | 0 | 10 | 10
5. Advice on secondary procurement under grant contracts | 0 | 3 | 3
6. Early warning assessment of all projects and follow-up
7. Progress reports check and follow-up | 0 | 10 | 10
8. Developing an indicative monitoring visit schedule | 0 | 15 | 15
9. Conducting monitoring visits | 0 | 12 | 12
10. Drafting monitoring visit reports and follow-up | 0 | 1 | 1
11. Keeping relevant up-to-date project information in electronic form | 0 | 6 | 6
Total | 3 | 92 | 92
V Programme monitoring
Activity | 2016 | 2017 | 2018
1. Preparation of Annual and Final Implementation Reports | 0 | 10 | 10
2. Cooperating with external, independent evaluators during programme implementation | 0 | 10 | 10
3. Proposing amendments and revisions to the programming documents | 3 | 15 | 15
4. Performing the duties of the secretariat of the JMC | 0 | 10 | 10
5. Supply of information to partner countries' OSs for their reporting duties | 0 | 3 | 3
Total | 3 | 48 | 48
VI Publicity, visibility and information
Activity | 2016 | 2017 | 2018
1. Preparing, monitoring, evaluating and updating the Communication Action Plan (CAP) | 0 | 10 | 10
2. Maintenance of a programme website | 0 | 10 | 10
3. Organising information and publicity events | 3 | 15 | 15
4. Arranging printed materials and other manufactured or electronic media | 0 | 10 | 10
5. Ensuring programme visibility and compliance with visual identity rules | 0 | 3 | 3
6. Establishing and maintaining databases and supplying data | 0 | 10 | 10
7. Handling media inquires | 0 | 15 | 15
Total | 3 | 73 | 73
VII Other
Activity | 2016 | 2017 | 2018
1. Preparation of documentation for and oversight of joint operations identified outside calls for proposals | 5 | 20 | 20
2. Reporting irregularities | 30 | 40 | 40
3. Recording and reporting exceptions | 10 | 10 | 10
4. Filing – physical documentation | 10 | 20 | 20
5. Filing – electronic documentation | 10 | 10 | 10
6. Client enquiries that do not fall into any of the above mentioned tasks | 3 | 3 | 3
7. Facilitating any monitoring or audit missions related to the TAGCs | 3 | 3 | 3
8. Addressing ad-hoc requests from EUDs related to programme implementation | 0 | 0 | 0
9. Attending coordination meetings with the OS | 0 | 2 | 2
Total | 71 | 108 | 108
Note on C48: ob1: 100 projects from mid 2009, 1 day for every 4
Note on D48: ob1: 100 projects from mid 2009, 1 day for every 4

## WL calculation - IM
Annex 2d: Workload calculation for indirect management mode (IM) For demostration and illustration purposes.
WORKLOAD CALCULATION FOR PROGRAMMES 2014-2020 OPERATING UNDER INDIRECT MANAGEMENT
Total number of days required for operations of the JTS per year: |  |  |  | 898.225
Total number of working days available per year: |  |  |  | 215
Required number of staff to adequately perform all tasks listed below: |  |  |  | 4.1778
Activity I : Management of technical assistance | Applicable (y/n) | Variable | Value of the variable | Total days
1. JTS work plan | y |  |  | 3
2. Reports on TA activities performed & costs incurred under the service contract(s) | y |  |  | 66
2.1 Timesheets (2 hrs x No of staff = 1 day x 12 months) | y | Number of Staff | 2 | 6
2.2 Narrative reporting - inception, interim and final reports (preparation 5 + control 2 days =7 days per report) | y | Number of reports | 3 | 21
2.3 Financial reporting - inception and progress reports (preparation of the financial report - 1 day + control 1 day = 2 days; assistance and discussion with auditors 2 days) | y | Number of reports | 3 | 8
2.4 Preparation of monthly reports (3 days for preparing each montly report) | y | Number of monthly reports | 9 | 27
3. Initiate drafting requests for payment & for amendments to the budget (16 payment requests a month=1 day x 12 months=12 days; 2 notification letters x 2 days = 4 days) | y | No of payment requests | 16 | 16
4. Ensuring visibility of outputs produced under TAGCs (contact with media 0.5 days x 12 months=6 days; agreeing design of materials with subcontractors - 3 days; attending beneficiaries' visibility events: 10 projects x 2 days=20 days; updating programme website: 2 days x 12 months=24 days) | y | No of projects implemented | 10 | 53
5. Prior approval of costs associated with the work of JTS staff (No of JTS staff x 2 requests x 0.25 hrs x 12 months) | y | No of travels per staff per month | 2 | 1.5
6. Claims for the payment of salaries of the JTS staff & costs associated with their work (No of JTS staff x 2 requests x 0.5 hrs x 12 months) | y | No of travels per staff per month | 2 | 3
7. Preparing procurement documentation for supplies or services under TAGCs (No of tenders x 3 days) | y | No of tenders | 10 | 30
8. Assistance in procuring supplies and/or services under TAGCs (No of tenders x 0.5 days) | y | No of tenders | 10 | 5
9. Managing contracts for supplies or services under TAGCs (No of tenders x 1 day) | y | No of tenders | 10 | 10
10. Preparing & negotiating the application form (incl. budget) for the subsequent TAGC and concluding the associated Grant/Service Contract | y |  |  | 10
Total Activity I : Management of technical assistance |  |  |  | 197.5
Activity II : Calls for proposals - launching phase | Applicable (y/n) | Variable | Value of the variable | Total days
1. Work Programme | y |  |  | 0.5
2. Call for Proposals Timetable | y |  |  | 0.5
3. Partner Search Forums (2 PSFs for each CfP x 5 days = 10 days) applicable only if launch of a CfP is planned for that year | y | No of PSFs | 2 | 10
4. Drafting calls for proposals and related documentation (application packs) applicable only if launch of a CfP is planned for that year | y |  |  | 10
5. Publication/upload to the programme website - applicable only if launch of a CfP is planned for that year | y |  |  | 0.1
6. Information sessions (No of information sessions per country x 2 days (1 day travel and 1 day organisation) * No of JTS staff + 0,5 days preparing materials, 0,5 day reporting and filing) - Applicable only if launch of a CfP is planned for that year | y | No of sessions per country | 2 | 8.5
7. Workshops for potential applicants (No of workshops per country x 3 days - 1 day travel and 2 days organisation * No of JTS staff + 5 days preparing materials, 1 day reporting and filing) | y | No of workshops per country | 2 | 18
8. Answering queries from interested applicants (80 queries x 0.5 hrs = 5 days) - Applicable only if launch of a CfP is planned for that year | y | Average No of queries | 10 | 0.625
9. Group consultation meetings with interested applicants (1 day travel x 1 day meeting x No of JTS staff) | n | No of meetings | 5 | 0
10. Individual consultation meetings with interested applicants (2 hours preparation and 2 hours meeting x 1 JTS staff) | n | No of meetings | 20 | 0
Total Activity II : Calls for proposals - launching phase |  |  |  | 48.225
Activity III : Calls for proposals - evaluation phase | Applicable (y/n) | Variable | Value of the variable | Total days
1. Drafting a proposal for the membership of the Joint Steering Committee/Evaluation Committee | n |  |  | 0.5
2. Arranging for hiring of assessors (1 day for preparing ToR that is required in any case and 2 days for preparing tender dossier and implement the tender procedure) | n | 1=tender used 2=other option | 1 | 0
3. Proposal for assessors | n |  |  | 0.5
4. Receipt, registration and storage of proposals | n |  |  | 5
5a. Secretarial duties for the opening session, administrative check (1.5 hrs per proposal for opening and admin check (including requests for clarifications) in case of an open call, or 45 mins per proposal in case of a restricted call + 1 day arranging JSC mtgs + 3 days compiling the report + (3 days travel + 3 days participating at the mtgs)*3 JTS staff) | n | Estimated No of proposals received | 100 | 0
5b. Secretarial duties for the concept note evaluation (0.5 hrs per proposal for checking evaluation grids and summarising the scores + 1 day arranging JSC mtgs + 3 days compiling the report + (3 days travel + 3 days participating at the mtgs) | n | 1=restricted call 2=open call | 1 | 0
5.c. Drafting letters notifying applicants on the status of their project (No of projects received x 0.5 days per letter for drafting and cross-checking) | n | Estimated No of proposals received | 100 | 0
5.d. Signing and dispatching letters notifying applicants (No of projects approved x 0.2 days per letter for signing, dispatching and checking if received) | n | Estimated No of proposals received | 100 | 0
6. Secretarial duties for the evaluation of full application forms (0.75 hrs per proposal for checking evaluation grids and summarising the scores + 1 day arranging JSC mtgs + 3 days compiling the report + (3 days travel + 3 days participating at the mtgs) | n | Estimated No of projects recommended | 15 | 0
7. Secretarial duties for the verification of eligibility, conclusions of the evaluation committee and production of the final evaluation report (0.5 hrs per proposal for verification of eligibility; no additional time for mtgs and reports since this step should always be merged with other steps of the evaluation) | n | 1=merged with step 1 2=merged with step 2 | 1 | 0
8. Drafting letters notifying applicants on the grant award or rejection of their project (No of projects received x 0.5 days per letter for drafting and cross-checking) | n | Estimated No of full applications evaluated | 30 | 0
9. Signing and dispatching letters notifying applicants (No of projects approved x 0.2 days per letter for signing, dispatching and checking if received) | n | Estimated No of full applications evaluated | 30 | 0
10. Budgetary clearing and contracting (1 day per proposal for creating initial budget clearing table + 2 days per proposal for concultations with the CA and the beneficiary; this includes time needed for setting up a meeting, if necessary) | n | Estimated No of projects recommended | 15 | 0
11. Publicising the award of grants | n |  |  | 0.5
12. Analysing statistical information on the Call for Proposals and measures for improving the quality of applications | y |  |  | 5
Total Activity III: Calls for proposals - evaluation phase |  |  |  | 5
Activity IV : Project monitoring | Applicable (y/n) | Variable | Value of the variable | Total days
1. Preparation of implementation package for project beneficiaries | y | 1= first time 2=revision | 2 | 5
2. Implementation of seminars for project beneficiaries (No of implementation seminars x 3 days (1 day travel and 2 day organisation) * No of JTS staff + 5 days preparing materials, 1 day reporting and filing) | n | No of seminars | 1 | 0
3. Opening and maintaining a file for each project (average 2 days per project during the entire implementation period) | y | No of projects implemented | 10 | 20
4. Help line for project beneficiaries (No of projects * (2 days commenting reports + 3 days various consultations)) | y | No of projects implemented | 10 | 50
5. Advice on secondary procurement under grant contracts (No of projects * 10 tenders requiring consultations * 1 day) | y | No of projects implemented | 10 | 100
6. Early warning assessment of all projects and follow-up (No of projects * 2 days during the entire implementation period) | y | No of projects implemented | 10 | 20
7. Progress reports check and follow-up (No of projects * 2 days during the entire implementation period) | y | No of projects implemented | 10 | 20
8. Developing an indicative monitoring visit schedule | y |  |  | 0.5
9. Conducting monitoring visits (3 visits a year per project: 1 day travel + 1 day compliance check + 1 day interviews for ROM monitoring) | y | No of projects implemented | 10 | 90
10. Drafting monitoring visit reports and follow-up (1 day preparing reports + 1 day follow up per each visit) | y | No of projects implemented | 10 | 60
11. Keeping relevant up-to-date project information in electronic form (0.5 days a project per year) | y | No of projects implemented | 10 | 5
Total Activity IV : Project monitoring |  |  |  | 370.5
Activity V : Programme monitoring | Applicable (y/n) | Variable | Value of the variable | Total days
1. Preparation of Annual and Final Implementation Reports (3 days gathering information, 15 days preparing the report, 2 days preparing the annexes) | y |  |  | 20
2. Cooperating with external, independent evaluators during programme implementation | y |  |  | 2
3. Proposing amendments and revisions to the programming documents | y |  |  | 5
4. Performing the duties of the secretariat of the JMC (No of JMC meetings * (1 day preparing documents, 2 days * No of JTS staff travel and organisation of a meeting, 2 days preparing and finalising meeting minutes)) | y | No of JMC meetings | 2 | 14
5. Supply of information to partner countries' OSs for their reporting duties | y |  |  | 5
Total Activity V : Programme monitoring |  |  |  | 46
Activity VI : Publicity, visibility and information | Applicable (y/n) | Variable | Value of the variable | Total days
1. Preparing, monitoring, evaluating and updating the Communication Action Plan (CAP) | y |  |  | 5
2. Maintenance of a programme website (during 12 months, 0.2 days per post) | y | Average No of posts in a month | 10 | 24
3. Organising information and publicity events (No of events * (3 days preparation + 1 day reporting + No of JTS staff * 1 day travel and 1 day organisation) | y | No of events | 1 | 8
4. Arranging printed materials and other manufactured or electronic media (a lump-sum value of 5 days a year, negotiating design with the company selected) | y |  |  | 5
5. Ensuring programme visibility and compliance with visual identity rules (during 12 months, 2 days per month) | y |  |  | 24
6. Establishing and maintaining databases and supplying data (2 days * 12 months) | y |  |  | 24
7. Handling media inquires (0.5 days * 12 months) | y |  |  | 6
Total Activity VI : Publicity, visibility and information |  |  |  | 96
Activity VII : Other | Applicable (y/n) | Variable | Value of the variable | Total days
1. Preparation of documentation for and oversight of joint operations identified outside calls for proposals (per operation: 10 days preparation of documentation, 20 days oversight of operations, 5 days revising their reports, 5 days visibility activities) | y | No of operations | 1 | 40
2. Reporting irregularities | y |  |  | 5
3. Recording and reporting exceptions | y |  |  | 5
4. Filing – physical documentation | y |  |  | 12
5. Filing – electronic documentation | y |  |  | 12
6. Client enquiries that do not fall into any of the above mentioned tasks (visitors, potential applicants calling, potential interships negotiations, open days, offering advertisements, communication with EC in Brussels, communication with EUDs, OSs, etc) | y |  |  | 24
7. Facilitating any monitoring or audit missions related to the TAGCs | y |  |  | 5
8. Addressing ad-hoc requests from EUDs related to programme implementation (e.g. collecting and providing information and documentation) | y |  |  | 5
9. Attending coordination meetings with the OS (all JTS staff attend meetings organised by the OS on regular basis - every 2 months: No of JTS staff x 1.5 days x 6 times a year) | y | No of staff | 3 | 27
Total Activity VII : Other |  |  |  | 135